Clark County

Pre-Disaster Mitigation Plan

2019-2024

Prepared by: First District Association of Local Governments

124 1st Avenue NW

Watertown, SD 57201

Phone:  605-882-5115

Fax:  605-882-5049

www.1stdistrict.org

For:  Federal Emergency Management Administration

##### TABLE OF CONTENTS

CHAPTER 1 – INTRODUCTION	5

- Introduction	5

- Authority for Pre-disaster Mitigation Plan	6

- Purpose	6

- Use of Plan	7

- Scope of Plan	7

- What is Hazard Mitigation	7

- Lake County Profile	9

  - Population	9

  - Social and Economic Description	11

  - Physical Description and Climate	12

  - Transportation and Utility Infrastructure	13

  - Medical and Emergency Services	14

CHAPTER 2 – PREREQUISITES	15

- Adoption by Local Governing Body	15

- Multi-jurisdictional Plan Participation	15

CHAPTER 3 – PLANNING PROCESS	19

- Background	19

- Documentation of Planning Process	20

  - Methodology	20

  - Planning Framework	20

  - Risk Identification & Assessment/Mitigation Strategy/Review of Plan	25

CHAPTER 4 – RISK ASSESSMENT	29

- Identification of Hazards	29

- Types of Natural Hazards in the PDM Jurisdiction Area	31

- Hazard Profile	35

  - Dam Failure	36

  - Drought and Wildfire	36

  - Earthquakes	38

  - Flood	39

  - Hail	39

  - Lightning	42

  - Tornado	42

  - Extreme Temperatures	43

  - Thunderstorms/High Winds	44

  - Winter Storms	47

  - Climate Change	49

- Assessing Vulnerability: Overview	49

- Assessing Vulnerability: National Flood Insurance Program Compliance	49

- Assessing Vulnerability: Repetitive Loss Properties	55

- Assessing Vulnerability: Severe Repetitive Loss Properties	56

- Assessing Vulnerability: Identifying Structures	57

- Assessing Vulnerability: Community Capabilities	65

- Assessing Vulnerability: Estimating Potential Losses	70

  - Flooding	77

  - Tornado	78

- Assessing Vulnerability: Analyzing Development Trends	79

- Unique or Varied Risk Assessment	81

CHAPTER 5 – MITIGATION STRATEGY	90

- Mitigation Overview	90

- Implementation of Mitigation Actions	128

CHAPTER 6 – PLAN MAINTENANCE	129

- Monitoring, Evaluating, and Updating the Plan	129

- Continued Public Participation/Involvement	129

- Annual Reporting Procedures	130

- Five-Year PDM Review	130

- Plan Amendments	131

- Incorporation into Existing Planning Mechanisms	131

- Potential Funding Sources	131

- Federal	132

- Local	135

- Non-Governmental	135

LIST OF TABLES

- 1.1:   Clark County Municipalities 	10

- 1.2:   Clark County Townships	11

- 2.1:   Plan Participants	15

- 2.2:   Dates of Plan Adoption by Jurisdiction	16

- 2.3:   Record of Participation 	17

- 3.1:   Participation in Plan Development 	21

- 3.2:   Opportunities for Public Comment	24

- 3.3:   Record of Review (Summary)	28

- 4.1:   Significant Hazard Occurrences	29

- 4.2:   Hazards Categorized by Likelihood of Occurrence 	30

- 4.3:   Presidential Disaster Declarations in Clark County	35

- 4.4:   Dam Locations in Clark County	36

- 4.5:   Clark County Ten Year Drought History	37

- 4.6:   Clark County Structural, Vehicle and Outside (Wildfire) Department   Responses	38

- 4.7:   Clark County 10-year Flood History	39

- 4.8:   Clark County 10-year Hail History 	40

- 4.9:   Clark County 10-year Tornado History 	42

- 4.10: Clark County 10-year History of Extreme Temperatures	43

- 4.11: Clark County 10-year History for Thunderstorms	44

- 4.12: Clark County 10-year History of Snow and Ice Storms………………………………………...47

- 4.13: Overall Summary of Vulnerability by Jurisdiction	50

- 4.14: Communities Participating in the National Flood Program, Clark County, SD	55

- 4.15: Clark County National Flood Insurance Program Statistics	56

- 4.16: Critical Structures in Clark County	58

- 4.17: Administrative and Technical Capabilities	66

- 4.18: Capabilities of Growth Guidance Instruments	68

- 4.19: Clark County (Rural Area) Estimated Potential Dollar Losses

to Vulnerable Structures	72

- 4.20: Town of Bradley Estimated Potential Dollar Losses to Vulnerable Structures	72

- 4.21: City of Clark Estimated Potential Dollar Losses to Vulnerable Structures	73

- 4.22:	Town of Garden City Estimated Potential Dollar Losses to Vulnerable Structures	73

- 4.23: Town of Naples Estimated Potential Dollar Losses to Vulnerable Structures	74

- 4.24: Town of Raymond Estimated Potential Dollar Losses to Vulnerable Structures	74

- 4.25: Town of Vienna Estimated Potential Dollar Losses to Vulnerable Structures……………….75

- 4.26: City of Willow Lake Estimated Potential Dollar Losses to Vulnerable Structures…………...75

- 4.27: Clark County Estimated Potential Dollar Losses to Vulnerable Structures	75

- 4.28: Utilities Estimated Potential Dollar Losses to Vulnerable Structures	76

- 4.29: HAZUS-MH Base Flood (1 Percent Chance) Loss Estimation Results (2011)	78

- 4.30: Clark County Annualized Losses from Tornadoes	78

- 4.31: Clark County (Unincorporated Area) Potential Floodplain

Development – By Land Use Type	79

- 4.32: City of Clark Potential Floodplain Development – By Land Use Type	80

- 4.33: Town of Vienna Potential Floodplain Development – By Land Use Type	80

- 4.34: City of Willow Lake Potential Floodplain Development – By Land Use Type	81

- 5.1:   Actions/Projects to Reduce Flood Risk through Policy Implementation	92

- 5.2:   Actions/Projects to Change the Characteristics or Impacts of Flood Hazards	94

- 5.3:   Actions/Projects to Reduce Loss Potential of Infrastructure to Flood Hazards	95

- 5.4:   Actions/Projects to Reduce Severe Weather Risk through Policy Implementation	96

- 5.5:   Actions/Projects to Change the Characteristics or Impacts of Severe Weather Hazards	97

- 5.6:   Actions/Projects to Reduce Loss Potential of Infrastructure to Severe Weather Hazards	98

- 5.7:   Actions/Projects to Reduce Fire and Drought Risk Through Policy Implementation	99

- 5.8:   Actions/Projects to Reduce Loss Potential of Infrastructure to Fire and Drought Hazards	100

- 5.9:   Actions/Projects to Change the Characteristics or Impacts of Fire and Drought Hazards	100

- 5.10: Technological Activities	101

- 5.11: Planning Activities	102

- 5.12: Administration/Coordination Activities	103

- 5.13: Proposed Mitigation Activities	107

LIST OF FIGURES

- 1.1:   Political Map 	9

- 4.1:	Clark County Flood Hazard Vulnerability Map	71

- 4.2:   Town of Bradley Hazard Vulnerability Map	82

- 4.3:   City of Clark Hazard Vulnerability Map	83

- 4.4:   Town of Garden City Hazard Vulnerability Map	84

- 4.5    Town of Naples Hazard Vulnerability Map	85

- 4.6:   Town of Raymond Hazard Vulnerability Map	86

- 4.7:   Town of Vienna Hazard Vulnerability Map	87

- 4.8:   City of Willow Lake Hazard Vulnerability Map	88

- 4.9:   Clark County Hazard Vulnerability Map………………………………………………………….89

- 5.1:   Clark County Potential Mitigation Project Map 	120

- 5.2:   Town of Bradley Potential Mitigation Project Map 	121

- 5.3:   City of Clark Potential Mitigation Project Map 	122

- 5.4:   Town of Garden City Potential Mitigation Project Map 	123

- 5.5:   Town of Naples Potential Mitigation Project Map	124

- 5.6:   Town of Raymond Potential Mitigation Project Map 	125

- 5.7:   Town of Vienna Potential Mitigation Project Map……………………………………………...126

- 5.8:   City of Willow Lake Potential Mitigation Project Map ………………………………………... 127

APPENDIX	136

- Appendix A:  Resolution of Adoption by Jurisdiction	137

- Appendix B:  PDM Planning Team Agendas, Sign-in Sheets	147

- Appendix C: Community Meeting and Sign in Sheets Jurisdiction	157

- Appendix D: Hazard Identification/Vulnerability Worksheets by Jurisdiction	181

- Appendix E: Township Vulnerable and Potential Mitigation Project Site Maps	204

- Appendix F: Codington-Clark Electric Co-Op Maps ………………………………………………...232

- Appendix G: Comprehensive Land Use Maps	260

- Appendix H: Review of 2013 PDM Mitigation Project Implementation	265

- Appendix I- References	269

CHAPTER 1

INTRODUCTION

INTRODUCTION

Clark County (County) is vulnerable to natural hazards that have the possibility of causing serious threat to the health, welfare, and security of our citizens. The cost of response and recovery, in terms of potential loss of life or loss of property, from potential disasters can be lessened when attention is turned to mitigating their impacts and effects before they occur or re-occur.

The Clark County Board of Commissioners, in conjunction with the South Dakota Office of Emergency Management and the Federal Emergency Management Agency (FEMA), has agreed to update this plan to assist all participating entities in the county in their mission to mitigate losses from natural hazards throughout Clark County, South Dakota and the communities located therein.

This plan is an update of the Pre-Disaster Mitigation Plan (PDM) that was developed by the County in 2013 and approved by FEMA in 2014. The document will serve as a strategic planning tool for use by the county and its communities in its efforts to mitigate against future disaster events. The plan identifies and analyzes the natural disasters that may occur in the County in order to understand the county’s vulnerabilities and propose mitigation strategies that minimize future damage caused by those hazards. This knowledge will help identify solutions that can significantly reduce threat to life and property. The plan is based on the premise that hazard mitigation works. With increased attention to mitigating natural hazards, communities can do much to reduce threats to existing citizens and avoid creating new problems in the future. In addition, many mitigation actions can be implemented at minimal cost.

In the past 10 years, there have been 22 major Disaster Declarations which have occurred fully or partially within the state of South Dakota, including 7 which occurred in 2010. Clark County is no stranger to natural and man-made disasters. All or portions of Clark County have been included in four Presidential Disaster Declarations in the last 10 years. In order to prevent and reduce the cost that is incurred by businesses, citizens, and property owners from these disasters, the Clark County Pre-Disaster Mitigation Plan developed. This plan identifies hazards that occur throughout Clark County and mitigation projects that will aid in preventing and reducing the effects of those disasters on the property and lives within. Special consideration has been given to critical infrastructure throughout the county.

This is not an emergency response or emergency management plan. Certainly, the plan can be used to identify weaknesses and refocus emergency response planning. Enhanced emergency response planning is an important mitigation strategy. However, the focus of this plan is to support better decision making directed toward avoidance of future risks and the implementation of activities or projects that will eliminate or reduce the risk for those that may already have exposure to a natural hazard threat.

AUTHORITY FOR PRE-DISASTER MITIGATION PLAN

In October of 2000, the Disaster Mitigation Act (DMA2K) was signed to amend the 1988 Robert T. Stafford Disaster Relief and Emergency Assistance Act. Section 322 (a-d) requires that local governments, as a condition of receiving federal disaster mitigation funds, have a pre-disaster mitigation (PDM) plan in place that:

- Identifies hazards and their associated risks and vulnerabilities;

- Develops and prioritizes mitigation projects; and

- Encourages cooperation and communication between all levels of government and the public.

The objective of this plan is to meet the hazard mitigation planning needs for the County and participating entities. Consistent with the Federal Emergency Management Agency’s guidelines, this plan will review all possible activities related to disasters to reach efficient solutions, link hazard management policies to specific activities, educate and facilitate communication with the public, build public and political support for mitigation activities, and develop implementation and planning requirements for future hazard mitigation projects.

PURPOSE

The County PDM is a planning tool to be used by the County, as well as other local, state and federal units of government, in their efforts to fulfill federal, state, and local hazard mitigation planning responsibilities; to promote pre and post disaster mitigation measures, short/long range strategies that minimize suffering, loss of life, and damage to property resulting from hazardous or potentially hazardous conditions to which citizens and institutions within the county are exposed; and to eliminate or minimize conditions which would have an undesirable impact on our citizens, economy, environment, or the well-being of the County. This plan will aid city, township, and county agencies and officials in enhancing public awareness to the threat hazards have on property and life, and what can be done to help prevent or reduce the vulnerability and risk of each County jurisdiction.

USE OF PLAN

The plan will be used to help the county and communities and their elected and appointed officials:

- Plan, design and implement programs and projects that will help reduce their community’s vulnerability to natural hazards

- Facilitate inter-jurisdictional coordination and collaboration related to natural hazard mitigation planning and implementation.

- Develop or provide guidance for local emergency response planning.

- Be compliant with the Disaster Mitigation Act of 2000.

SCOPE OF PLAN

- Provide opportunities for public input and encourage participation and involvement regarding the mitigation plan.

- Identify hazards and vulnerabilities within the county and local jurisdictions.

- Combine risk assessments with public and emergency management ideas.

- Develop goals based on the identified hazards and risks.

- Review existing mitigation measures for gaps and establish projects to sufficiently fulfill the goals.

- Prioritize and evaluate each strategy/objective.

- Review other plans for cohesion and incorporation with the PDM.

- Establish guidelines for updating and monitoring the plan.

- Present the plan to the Clark County Commissioners and the participating communities within the county for adoption.

WHAT IS HAZARD MITIGATION?

Hazard mitigation is defined as any cost-effective action(s) that has the effect of reducing, limiting, or preventing vulnerability of people, property, and the environment to potentially damaging, harmful, or costly hazards. Hazard mitigation measures, which can be used to eliminate or minimize the risk to life and property, fall into three categories. First are those that keep the hazard away from people, property, and structures. Second are those that keep people, property, and structures away from the hazard. Third are those that do not address the hazard at all but rather reduce the impact of the hazard on the victims such as insurance. This mitigation plan has strategies that fall into all three categories.

Hazard mitigation measures must be practical, cost effective, and environmentally and politically acceptable. Actions taken to limit the vulnerability of society to hazards must not in themselves be costlier than the value of anticipated damages.

The primary focus of hazard mitigation actions must be at the point at which capital investment decisions are made and based on vulnerability. Capital investments, whether for homes, roads, public utilities, pipelines, power plants, or public works, determine to a large extent the nature and degree of hazard vulnerability of a community. Once a capital facility is in place, very few opportunities will present themselves over the useful life of the facility to correct any errors in location or construction with respect to hazard vulnerability. It is for these reasons that zoning and other ordinances, which manage development in high vulnerability areas, and building codes, which ensure that new buildings are built to withstand the damaging forces of hazards, are often the most useful mitigation approaches a jurisdiction can implement.

Previously, mitigation measures have been the most neglected programs within emergency management. Since the priority to implement mitigation activities is generally low in comparison to the perceived threat, some important mitigation measures take time to implement. Mitigation success can be achieved, however, if accurate information is portrayed through complete hazard identification and impact studies, followed by effective mitigation management. Hazard mitigation is the key to eliminating long-term risk to people and property in South Dakota from hazards and their effects. Preparedness for all hazards includes:  response and recovery plans, training, development, management of resources, and mitigation of each jurisdictional hazard.

This plan evaluates the impacts, risks and vulnerabilities of natural hazards within the jurisdictional area of the entire county. The plan supports, provides assistance, identifies and describes mitigation projects for each of the local jurisdictions who participated in the plan update. The suggested actions and plan implementation for local governments could reduce the impact of future natural hazard occurrences. Lessening the impact of natural hazards can prevent such occurrences from becoming disastrous but will only be accomplished through coordinated partnership with emergency managers, political entities, public works officials, community planners and other dedicated individuals working to implement this program.

# Clark County Profile

Population

Clark County is located in eastern South Dakota. It borders Day County to the north, Codington and Hamlin to the east, Kingsbury and Beadle to the south, and Spink to the west. The county has a geographic area of 967 square miles and its Census 2010 population was 3,691, which averages to 3.9 people per square mile. Figure 1.1 contains a map of Clark County

Figure 1.1 Political Map

Just under twenty-two percent of the population is sixty-five or older. Education levels of persons 25% and older include 43.8% are high school graduates and 19.9% percent college level.  The county seat is City of Clark, which is situated at the intersection of US Highway 212 and County Road 46.  Table 1.1 shows the population and number of housing units of the county’s municipalities.

Table 1.1:  Clark County Municipalities

| Name | Population | Location | Elevation | Housing Units |
| --- | --- | --- | --- | --- |
| Bradley | 72 | 45.09 -97.58 | 1,814 | 53 |
| Clark | 1,139 | 44.88 -97.73 | 1,795 | 627 |
| Garden City | 53 | 44.95 -97.58 | 1,857 | 35 |
| Naples | 41 | 44.77 -97.51 | 1,785 | 12 |
| Raymond | 50 | 44.91 -97.93 | 1,457 | 38 |
| Vienna | 45 | 44.70 -97.50 | 1,834 | 22 |
| Willow Lake | 263 | 44.62 -96.63 | 1,781 | 129 |
| Unincorporated Areas | 2,028 |  |  |  |
| Clark County | 3,691 | 44 3' 3.1'' N 97 7' 45.8'' W | 1,785 | 1,710 |

Source: 2010 Census, www.latlong.net, http://elevation.maplogs.com/

Table 1.2 lists the 16 County Townships and populations. The County has experienced a relatively steady population since the 1920s.

Table 1.2:  Clark County Townships

| Township | Population | Township | Population |
| --- | --- | --- | --- |
| Blaine | 36 | Cottonwood | 84 |
| Spring Valley | 40 | Warren | 38 |
| Ash | 32 | Woodland | 63 |
| Thorp | 46 | Maydell | 51 |
| Eden | 59 | Mount Pleasant | 270 |
| Garfield | 60 | Raymond | 50 |
| Logan | 43 | Lincoln | 94 |
| Day | 85 | Elrod | 90 |
| Foxton | 51 | Merton | 51 |
| Darlington | 50 | Fordham | 111 |
| Richland | 61 | Hague | 38 |
| Lake | 79 | Pleasant | 166 |
| Washington | 67 | Collins | 129 |
| Rosedale | 71 |  |  |

Source: 2010 ACS US Census Bureau

Social and Economic Description

Agriculture is the primary business activity in Clark County. While the number of farm and ranching units has decreased over the years, the size of each unit has increased dramatically. The number of acres farmed or ranched has remained stable throughout the years. Most non-agricultural employment is in education, health care, or service industries. Hunting and fishing are popular with residents and non-residents alike. These activities, along with camping and lake use recreation, form the base for most tourism opportunities.

Unemployment rates in South Dakota have slowly declined over the last five years to around 3.5%, while Clark County has an estimated 3.3% unemployment rate over the last five years. According to the 2013-2017 American Community Survey 5-year estimates, approximately 15.5% of the population of Clark County falls below the poverty line. The City of Clark is the largest community in Clark County. Clark and Willow Lake have k-12 school facilities located in their county.

Physical Description and Climate

The majority of the land area within Clark County is farmland consisting of grassland, pasture and cropland. Roughly half of the county lies within the Big Sioux River watershed, which drains in a southeasterly direction. As the Coteau des Prairie slopes downward to the west (approximately the western third of the county) drains into the James River watershed. Clark County is located within the region generally classified as mild and dry continental or Steppe with four well-defined seasons. The weather can be quite variable with large day to day temperature changes particularly from the fall to the spring. Days with severe winter cold and summer heat are typical.

Normally the temperature is moderate until the beginning of July, after which short, hot periods are experienced until the end of August. The freeze-free period is the number of days between the average last occurrence of freezing temperatures in the spring and the average first occurrence of 32 degrees F or lower in the fall. The length of the freeze-free period approximates the length of the growing season which ranges from 130 days or more between May 21st and September 21st. Topography and local weather conditions can produce subfreezing temperatures at the ground surface while the air temperature a few feet above the ground remains above 32 degrees F.

Annual average precipitation is 25.75 inches, with over 64% of the precipitation falling from May through September. Precipitation can vary significantly from year to year, and location to location within a given year. The heaviest most intense precipitation often occurs with localized downpours associated with thunderstorms in June through August. Significant flash flooding can result from these downpours with over 3 inches of precipitation reported in a few events. Widespread heavy precipitation events of 1 to 2 inches can occur every few years and is most common from April through June and September through early November.

Average winter snowfall ranges up to 37 inches. The heaviest snowstorms often occur from late March through May or mid-October to mid-November. These storms can produce more than 12 inches of snow and are often made more severe as temperatures are warmer, and therefore the snow is heavier and more difficult to travel in and remove. These storms are often accompanied by high winds resulting in blizzard conditions. In spring these storms can coincide with the calving season resulting in livestock loss. Mid-winter snowstorms in general produce less than 6 inches of snow, but heavier amounts to 19 inches or more have occurred. Despite the generally lighter amounts and drier snow, high winds can result in blizzard conditions. Even without falling snow, in the colder conditions of midwinter, high winds can pick up loose snow, resulting in local ground blizzards.

Severe thunderstorms are common from June into early September. Typically, the greatest hazards associated with these thunderstorms are very high winds and large hail. Damage to structures and crops occurs every summer from these storms. Tornadoes have been reported but are relatively rare.

An unavoidable element of the climate in Clark County is wind. Average annual wind speed in Clark County is 19.7 mph. The average and peak sustained winds tend to be stronger over higher more exposed terrain. The highest sustained winds tend to occur in the spring and fall, with sustained winds over 40 mph occurring every year. The highest wind gusts are often associated with thunderstorms during the summer, with gusts over 60 mph occurring every year.

For the purposes of this hazard assessment and mitigation plan, weather is of interest when it threatens property or life and thus becomes a hazard. The National Weather Service (NWS) provides short-term forecasts of hazardous weather to the public. In addition to issuing tornado and severe thunderstorm watches the NWS also produces regularly-scheduled severe weather outlooks and updates on various forms of hazardous weather including heavy rain and winter storms.

Transportation and Utility Infrastructure

Clark County meets its current transportation needs through a mixture of state and federal highways, railroads, county roads, municipal road systems and township roads. The rural road system performs two basic functions: (1) providing general mobility for the residents in rural areas, and (2) accommodating the movements of agricultural products to market. The rural transportation system was not designed to accommodate large volumes of daily traffic.

Major transportation infrastructure in the county includes roads, railroads, and an airfield. South Dakota State Highway(s) 20, 25, 28, and US Highway 212 provide the main transportation routes through Clark County. The bulk of the transportation infrastructure includes county highways and township roads that are used for rural transportation involving residents, agricultural products and other commodities.

In Clark County, the transportation choices are limited to mostly private automobiles traveling over state and federal highways and county roads. Clark County’s road system consists of 1,608 miles of road, 1,072 miles of gravel road, 256 miles of hard-surfaced roads, 280 minimum maintenance roads, and 21 bridges.

Clark County has one small airport located in Clark. The airport is used primarily by local pilots, crop sprayers and other light aircraft. The airport does not have any nav-aid service but provides some flight service capabilities.

Clark Rural Water System (CRWS) serves some of the incorporated communities and the majority of rural residences in Clark County. CRWS serves the communities of Raymond and Bradley in Clark County. All other municipalities rely upon shallow aquifer/well systems.

Although residential growth is not expected to be significant in the county, new developments need to be controlled through planning and development guidelines concerning waste and wastewater collection systems. Central sewer collection systems are used by Bradley, Clark, Garden City, Raymond, and Willow Lake. All other incorporated municipalities use septic systems as is common in rural portions of the County.

Electric power is provided to rural county residents and people in the communities by Codington-Clark Electric Co-Op and Northwestern Energy. The primary telephone companies serving the County’s population is Interstate Telephone Company. Cellular phone service is available in most parts of the county, but there are still places in the county where signals are weak.

Medical and Emergency Services

Emergency and medical services are available within the county. The main ambulance service is provided by Clark County Ambulance Service based in Clark, SD. Ambulance Services in Codington, Kingsbury, Hamlin, Spink, and Day Counties provide emergency services to portions of the County. Sanford Health Clinic serves as the main healthcare provider in Clark County alongside Clark Care and Rehabilitation Center. Nursing and assisted living centers are located within Clark and Willow Lake. Clark County 911 services are dispatched through the City of Watertown Police Department and relayed to the Clark County Sheriff’s Office.

The Clark County Sheriff’s Department provides law enforcement for the entire county. Additional law enforcement agencies include the Clark Police Department, Willow Lake Police Department, South Dakota Highway Patrol and South Dakota Game, Fish and Parks.  The communities of Bradley, Clark, Garden City, Raymond, Vienna, and Willow Lake have their own volunteer fire departments.

CHAPTER 2

PREREQUISITES

ADOPTION BY LOCAL GOVERNING BODY

The local governing body, that oversees the update of the Clark County Pre-Disaster Mitigation Plan, is the Clark County Board of Commissioners. The Commission has tasked the Clark County Emergency Management Office with the responsibility of ensuring that the PDM is compliant with Federal Emergency Management Agency (FEMA) Guidelines and corresponding regulations.

MULTI-JURISDICTIONAL PLAN PARTICIPATION

Requirement 201.6(c)(5).  Local Mitigation Plan Review Tool – E2.

Requirement 201.6(c)(5).  Local Mitigation Plan Review Tool – E1.

This plan is a multi-jurisdictional plan which serves the entire geographical area located within the boundaries of Clark County, South Dakota. The County has seven incorporated municipalities. Less than a majority of the incorporated municipalities located within the County elected to participate in the planning process and update of the 2013 PDM. Table 2.1 shows the participating local jurisdictions include the following municipalities:

Table 2.1:  Plan Participants

Clark County

Town of Bradley*

City of Clark

Town of Garden City*

Town of Naples*

Town of Raymond

Town of Vienna*

City of Willow Lake

Codington-Clark Electric Co-op

*Did not participate in 2013 PDM Update

Non-participating communities are still eligible for hazard mitigation funding, however, may not directly apply for assistance. Instead any assistance would need to be applied for on behalf of the non-participating communities by Clark County.

Unincorporated villages of Carpenter and Crocker and the 27 townships are not direct participating entities in the plan. All villages are governed by the local township boards and are served by the County whenever necessary.

The Clark County Commission and each of the listed participating municipalities will pass resolutions to adopt the updated PDM. The dates of adoption by resolution for each of the jurisdictions are summarized in Table 2.2.

Table 2.2: Dates of Plan Adoption by Jurisdiction

| Jurisdiction | Date of Adoption |
| --- | --- |
| Bradley | June 5, 2019 |
| Clark | June 3, 2019 |
| Garden City | June 3, 2019 |
| Naples | May 16, 2019 |
| Raymond | May 7, 2019 |
| Vienna | May 16, 2019 |
| Willow Lake | June 10, 2019 |
| Clark County | May 20, 2019 |
| Codington-Clark Electric Co-Op | May 23, 2019 |

All of the participating jurisdictions were involved in the plan update. Representatives from each municipality, the County, the Townships, local fire departments, education facilities, utility providers, businesses and media were invited to be members of the Pre-Disaster Mitigation Team. Those in attendance provided valuable perspective on the changes required for the plan. All representatives in attendance took part in the risk assessment exercise at the August 28, 2018 kickoff meeting.

Representatives in attendance took information from the PDM Planning Team planning meetings back to their respective councils/organizations and presented the progress of the plan update. First District Association of Local Governments (First District) staff also presented progress reports when meeting individually with communities. The local jurisdictions/organizations will pass the resolutions upon FEMA approval of the PDM update. The Resolutions are included in the Appendix.

Table 2.3 was derived to help define “participation” for the local jurisdictions who intend on adopting the plan. To be considered “participating”, each jurisdiction must have at least seven of the ten participation requirements fulfilled.

Table 2.3: Record of Participation

| Nature of Participation | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County | Codington-Clark Electric Co-Op |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Attended Meetings or work sessions (a minimum of 1 meeting will be considered satisfactory). | X | X | X | X | X | X | X | X | X |
| Submitted inventory and summary of reports and plans relevant to hazard mitigation. | X | X | X | X | X | X | X | X | X |
| Submitted the Risk Assessment Worksheet. | X | X | X | X | X | X | X | X | X |
| Submitted description of what is at risk (including local critical facilities and infrastructure at risk from specific Hazards worksheet) | X | X | X | X | X | X | X | X | X |
| Nature of Participation | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County | Codington-Clark Electric Co-Op |
| Submitted a description or map of local land-use patterns (current and proposed & expected) |  | X |  |  |  | X | X | X |  |
| Developed goals for the community. | X | X | X | X | X | X | X | X | X |
| Developed mitigation actions with an analysis/explanation of why those actions were selected. | X | X | X | X | X | X | X | X | X |
| Prioritized actions emphasizing relative cost-effectiveness. | X | X | X | X | X | X | X | X | X |
| Reviewed and commented on draft Plan. | X | X | X | X | X | X | X | X | X |
| Hosted opportunities for public involvement (allowed time for public comment at a minimum of 1 city council meetings after giving a status report on the progress of the PDM update) | X | X | X | X | X | X | X | X |  |

CHAPTER 3

PLANNING PROCESS

BACKGROUND

The effort that led to the development of this plan is part of the larger, integrated approach to hazard mitigation planning in South Dakota that is led by the South Dakota Office of Emergency Management. Production of the plan was the ultimate responsibility of the Clark County Emergency Management Director, who served as the county’s point of contact for all activities associated with this plan. Input was received from the PDM Planning Team that was put together by the Emergency Management Director and whose members are listed below in Table 3.1.

The plan itself was written by an outside contractor, First District Association of Local Governments (First District) of Watertown, South Dakota, one of the state’s six regional planning entities. The office has an extensive amount of experience in producing various kinds of planning documents, including municipal ordinances, land use plans, and zoning ordinances, and it is an acknowledged leader in geographic information systems (GIS) technology in South Dakota. The following staff members of the First District Association of Local Governments were involved in the production of the plan. Thomas Nealon, Planner was the project manager of the plan. Nealon attended the PDM Planning Team meetings as the plan was being developed. Assisting Mr. Nealon was Amy Arnold, Geographic Information Systems Planner, who produced all the maps for the plan, Luke Muller, Senior Planner, directed the floodplain risk analysis, and completed the county land cover analysis discussed in the previous chapter. Meeting coordination performed by Project Intern Mark McLaughlin. Several other individuals at the state level provided additional support and information that was quite useful. They include:

- Marc Macy, South Dakota National Flood Insurance Program Coordinator – provided classification and information regarding value and number of flood insurance policies and claims, as well as guidance and direction as the plan was being developed.

- SD State Fire Marshall Office – provided information on fire calls in the county.

- Tim Schaal, South Dakota State Dam Inspector – provided information on dams located in the county.

- Greg Pollreisz, SD Department of Transportation – provided bridges and road mileage information for county.

DOCUMENTATION OF THE PLANNING PROCESS

Methodology

Mitigation planning is a process that communities use to identify policies, activities, and tools to implement mitigation actions. The process that was used to develop this plan consisted of the following steps:

- Planning Framework

- Risk Identification and Assessment

- Mitigation Strategy

- Review of Plan

- Plan Adoption and Maintenance

Planning Framework

The planning framework component identified five objectives:

- Develop Plan to Plan;

- Establish initial PDM Planning Team;

- Define Scope of the Plan;

- Identify Governmental Entities/Stakeholders; and

- Establish PDM Planning Team

Prior to receiving funding, a public meeting was held at the Clark County Courthouse to inform the public about the required PDM update. Funding from FEMA and the South Dakota Office of Emergency Management to prepare the mitigation plan was received by the county in June of 2018. Once funding was secured, the first task was to identify those entities/stakeholders that would have direct and indirect interests in the update of the PDM. the Clark County Emergency Management Director and the First District identified the PDM Planning Team and began to discuss the strategy to be used to develop the plan

Prior to the first public informational meeting, notice was electronically provided to all adjoining counties’ emergency management directors and published in the newspaper. The Clark County Emergency Management Director wrote letters to all the stakeholders, community organizations, municipalities, townships, utility providers and emergency responders and concerned residents who might wish to volunteer their time and serve on the PDM Planning Team and to those who would act as a resource for the PDM Planning Team.  The letters also included a brief description of the PDM planning process. Public input was solicited via notices regarding the PDM planning process in local media outlets and via the Internet.

Each individual contacted for the PDM Planning Team had at least one of the following attributes to contribute to the planning process:

- Significant understanding of how hazards affect the county and participating jurisdictions.

- Substantial knowledge of the county’s infrastructure system.

- Resources at their disposal to assist in the planning effort, such as maps or data on past hazard events.

Table 3.1 lists the PDM Planning Team members, and it includes their attendance at the planning meetings, all of which were open to the public, that were held as the plan was being developed. An agenda was sent out to the PDM Planning Team prior to each meeting, and the meeting minutes were sent to them afterward to keep everybody informed of what was discussed and any decisions that were made.

Table 3.1: Participation in Plan Development

| Last Name | First Name | Entity Represented | Meeting Attendance |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Meeting 1 | Meeting 2 | Meeting 3 |  |
| McGraw | Robert | Clark County Sheriff’s Office/LEPC | x | x | x |  |
| Gravning | Mike | Clark County Emergency Management | x | x | x |  |
| Lattrell | Jackie | City of Clark | x |  |  |  |
| Ries | Carrie | Town of Raymond | x |  |  |  |
| Warkenthien | Jeanette | Town of Garden City &Town of Bradley |  |  |  |  |
| Madsen | Heidi | City of Willow Lake | x |  |  |  |
| Lewendowski | James | Town of Vienna |  |  |  |  |
| Snyman | Kerri | Town of Naples |  |  |  |  |
| Lee | Chris | Willow Lake School District |  |  |  |  |
| Warren | Luanne | Clark School District |  |  |  |  |
| Kaufman | Terry | Clark Rural Water Systems |  |  |  |  |
| Johnson | Bob | Codington-Clark Electric Co-op | x | x | x |  |
| Seefeldt | Jeff | Clark Fire Department | x | x | x |  |
| Zantoe | Rick | Willow Lake Fire Department |  |  | x |  |
| Vandersnick | Matt | Vienna Fire Department |  |  |  |  |
| Fritz | Chad | Raymond Fire Department | x |  |  |  |
| Loomis | Doug | Garden City Fire Department |  |  |  |  |
| Matthews | Clint | Bradley Fire Department | x |  |  | x |
| Hallauer | Joyce | Prairie Lakes SD Health Care Coalition | x |  |  | x |

Leadership and guidance in the planning effort and at the planning meetings was provided by the First District staff and the Clark County Emergency Management Director. An agenda was distributed to each PDM Planning Team member prior to each meeting, but free-flowing discussion was always encouraged. When PDM Planning Team members had questions about a topic of discussion, either First District staff or the Emergency Management Director would provide research and input.

The planning process associated with the plan’s development was relaxed and informal. No subcommittees were formed, and all decisions were made by mutual consensus of the PDM Planning Team members. Everyone’s opinion was respected, and nobody was discouraged from voicing their opinion nor made to feel any less important than anyone else.

As the PDM Planning Team was being assembled, arrangements were made for the first PDM Planning Team meeting, which took place at the Clark County Courthouse in Clark on August 28th, 2018. An agenda was distributed to prospective PDM Planning Team members. The Appendix includes a copy of each meeting agenda, the signup sheet from each meeting, and the minutes from each meeting.

Those who attended the August 2018 meeting for the PDM update were asked to volunteer to serve on the PDM Planning Team. The PDM Planning Team was tasked with fostering coordination between the various entities involved; reviewing the drafts and providing comments after First District Staff drafted changes to the existing plan. There were no external contributors such as contractors, other than the local utility providers. Each of the local jurisdictions were represented by a member of their respective councils.

The first meeting of the PDM Planning Team served to introduce the participants to the concept of mitigation planning; why the plan was being updated and how the process would proceed in the months to come (scheduling, assigning responsibilities, etc.). The meeting also included a review of the existing plan, which led to two important decisions. First, it was the consensus opinion of the PDM Planning Team that a comprehensive rewrite of the plan would be needed.

The PDM Planning Team decided that:

- The 2013 PDM plan did include the necessary requirements found in the current Local Hazard Plan Review Tool (2011). To ensure that the updated plan included everything required by the plan review tool, the PDM Planning Team and community meetings used the plan review tool to guide the discussions. The 2013 PDM plan was then compared to the plan review tool and any portion of the plan that was not needed to fulfill the tool requirements was eliminated and deficiencies were noted as areas of focus.

- More information and data regarding the risk assessment was needed, more informative tables and maps would be helpful, and the man-made hazards sections were deleted.

- The risk identification and assessment as well as the identification of critical infrastructure and local municipal goals and objectives should be completed by the First District prior to the next meeting of the PDM Planning Team.

The representatives from the municipalities were asked to share the progress of the plan at their council meetings and to ensure that those attending the council meetings were aware that they are invited to make comments on and participate in the process of updating the new plan.  Comments provided by residents at the community and PDM Planning Team meetings were collected and incorporated into the plan.

The public was provided several opportunities to comment on the plan during the drafting stages at the PDM Planning Team meetings, and local community meetings. Primarily, public input included the involvement in hazard assessment and identification of mitigation projects. Those who were most involved were the representatives PDM Planning Team and representatives from the municipalities. The municipalities put the PDM update on the agenda at their regular meeting and allowed people to comment at the meeting. Table 3.2 identifies the location and date of each opportunity that was provided for the public to comment and how it was advertised.

Table 3.2: Opportunities for Public Comment

| Location of Opportunity | Date | Type of Participation |  | How Was Meeting Advertised |  |
| --- | --- | --- | --- | --- | --- |
|  |  | City Council Town Board County Commission Meeting | PDM Meeting | Public Notice | Website |
| Bradley | 09/19/2018 | x |  | x |  |
|  | 06/05/2019 | x |  | x |  |
| Clark | 09/19/2018 | x |  | x |  |
|  | 06/03/2019 | x |  | x |  |
| Garden City | 09/20/2018 | x |  | x |  |
|  | 06/03/2019 | x |  | x |  |
| Naples | 11/05/2018 | x |  | x |  |
|  | 05/16/2019 | x |  | x |  |
| Raymond | 11/05/2018 | x |  | x |  |
|  | 05/07/2019 | x |  | x |  |
| Vienna | 10/11/2018 | x |  | x |  |
|  | 05/16/2019 | x |  | x |  |
| Willow Lake | 10/08/2018 | x |  | x |  |
|  | 06/10/2019 | x |  | x |  |
| Clark County | PDM Grant Application 05/02/2017 | x |  | x |  |
|  | 08/28/2018 |  | x | x |  |
|  | 11/13/2018 |  | x | x |  |
|  | 01/10/2019 |  | x | x |  |
|  | 05/20/2019 | x |  | x |  |

Risk Identification & Assessment/Mitigation Strategy/Review of Plan

Requirement 201.6(b)(1).  Local Mitigation Plan Review Tool – A3.

Requirement 201.6(c)(1).  Local Mitigation Plan Review Tool – A1.

Requirement 201.6(b)(3).  Local Mitigation Plan Review Tool – A4.

The Risk Identification and Assessment component identified three objectives: collect and organize Data, develop GIS data, and analyze data. The Mitigation strategy component identified five objectives: Review the 2013 PDM and other plans, formation of goals/objectives, compile existing resources to accomplish goals/objectives, Public review of goals/objectives, and PDM Planning Team Review of goals/objectives.  The Review of PDM component identified three objectives: writing of PDM, public review of PDM, and PDM Planning Team review of PDM.

The meeting included a review of the hazards identified in the State of South Dakota Hazard Mitigation Plan and that risk assessment portion of the 2013 PDM plan. Based upon the discussions and information provided at the first meeting, it was determined that the 2013 PDM Risk Assessment and Mitigation Strategies were insufficient and that a comprehensive rewrite of the entire sections were needed. First District Staff revised or created the Introduction, Pre-requisites, Risk Assessment, Mitigation Strategy, and Plan Implementation components of the PDM. First District also met with each participating jurisdiction to review proposed mitigation actions, including estimated costs, responsibility and priority.

Prior to the second PDM Planning Team meeting, First District Staff met with the participating municipalities and mailed requests to the Clark County Townships to identify hazards and critical facilities, assess vulnerability, discuss development trends, and develop mitigation goals. Meeting dates are referenced in Table 3.2. Staff members from Clark County, Clark County Townships, rural electric, water and wastewater providers were asked to identify hazards, critical facilities and assess vulnerability within Clark County. In addition, they were asked to develop mitigation activities and review these items with their respective governing body (if applicable). First District staff also conducted research regarding the history of disaster events in the county, including events that had occurred since the original plan was developed.

First District also conducted a technical review of existing documents. This review incorporated existing plans, studies, reports, technical information, zoning and flood damage prevention ordinances into the PDM Update. It should be noted that most of the planning documents of each of the communities had been previously developed by the First District. However, some of the smaller communities did not have such planning documents. The previous Pre-Disaster Plan was done by an outside consultant and thus First District cannot speak to the quality of the work. Additionally, the 2013 PDM plan was used as a resource for the new plan because most of the natural hazard profile research had already been completed when it was drafted. In addition to the PDM, the First District reviewed several other existing documents including but not limited to the State of South Dakota 2014 Hazard Mitigation Plan, Clark County 2018 Hazardous Materials Plan, and Flood Insurance Rate Maps for the local jurisdictions. A summary of the technical review and incorporation of existing plans is included in Table 3.3.

The list of hazards that the PDM Planning Team decided to focus on is presented in Chapter 4. The profile included information from each of the participating jurisdictions about how the hazard affected their community. Discussion also occurred regarding the existing strategies being used to mitigate each hazard, with a particular emphasis on the critical and essential facilities in each community.

The PDM Planning Team also dealt with the Mitigation Strategy at the August 2018 meeting. Formation of the strategy began with a review of the results of the risk assessment, which led to discussion about the goals to be achieved with the mitigation plan. The list of goals is included in Chapter 5.

At the second meeting on November 13, 2018, the PDM Planning Team reviewed the draft prepared by the First District. First District staff also provided an overview of the information regarding critical facilities, risk identification, hazard vulnerability and mitigation goals identified by the County’s municipalities.

At the meeting, the PDM Planning Team identified goals for the PDM Update and compared those goals to those identified in the 2013 PDM plan. In addition, the PDM Planning Team reviewed the list of proposed actions included in the previous mitigation plan and discussion followed about the progress that had been made on implementing the actions. Specific mitigation actions recently identified by the participating jurisdictions were also discussed.

The rest of the meeting was spent prioritizing the mitigation actions and discussing how the plan would be implemented. It was emphasized that cooperation between the county and the participating jurisdictions was especially important, and discussion occurred about how this could best be achieved. Representatives from the jurisdictions were made aware of the critical role they needed to play to ensure the success of the mitigation strategy, such as implementing specific mitigation actions. Nealon emphasized the importance of ensuring that no local decisions be made or actions taken contrary to the goals of this plan.  Also, responsible parties were identified for reporting on progress being made to implement the proposed mitigation actions, for evaluating the plan’s overall effectiveness, and for getting the public more involved in the planning process.

At the end of the meeting the First District was instructed to conduct an internal review of the document and forward the document to the South Dakota Office of Emergency Management for their review and comment. The draft plan was also to be posted on the First District website and notices regarding the draft plan emailed to the emergency managers in the adjoining counties of: Codington, Hamlin, Kingsbury, Beadle, Spink, and Day.  Everyone who received an email notice regarding the plan draft was allowed forty-five days to comment on the draft.

The final meeting of the PDM Planning Team was subsequently held on December 27, 2018 to review and discuss final draft as amended based upon comments from the planning team and communities.  At the meeting the PDM Planning Team recommended that the plan be submitted to FEMA. The final draft of the plan was again posted on the First District Association of Local Governments and Clark County websites.

Table 3.3: Record of Review (Summary)

| Existing Program/Policy/Technical Documents |  |  | Local Jurisdictions |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Bradley | Clark |  | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| Comprehensive Plan |  | x |  |  |  |  | x | x | x |
| Capital Improvement Plan |  |  |  |  |  |  |  |  |  |
| Flood Damage Prevention Ordinance |  |  |  |  |  |  |  |  | x |
| Economic Development Plan | x | x |  | x | x | x | x | x | x |
| Transportation Plan |  | x |  |  |  |  | x | x | x |
| Storm water Management/ Drainage Plan |  |  |  |  |  |  |  |  |  |
| Flood Insurance Studies or Engineering studies for streams |  | x |  |  |  | x |  | x | x |
| Hazardous Materials Plan |  |  |  |  |  |  |  |  | x |
| Emergency Operations Plan |  |  |  |  |  |  |  |  | x |
| Zoning Ordinance |  | x |  |  |  |  | x | x | x |
| Building Code |  |  |  |  |  |  |  |  |  |
| Site Plan Review |  | x |  |  |  |  | x | x | x |
| Subdivision Ordinance |  | x |  |  |  |  |  | x |  |
| Drainage Ordinance |  |  |  |  |  |  |  |  |  |
| Existing Land Use maps |  | x |  |  |  |  | x | x | x |
| Aquifer Protection Ordinance |  |  |  |  |  |  |  |  | x |
| State Hazard Mitigation Plan | x | x |  | x | x | x | x | x | x |

CHAPTER 4

RISK ASSESSMENT

IDENTIFICATION OF HAZARDS

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B1.

In this chapter, the hazards that were identified by the PDM Planning Team as having the most significance for the County are analyzed and listed below.  As part of the analysis, various maps and tables were produced and are included within this chapter. The planning participants began the risk assessment process by reviewing the State of South Dakota Hazard Mitigation Plan. The PDM Planning Team also reviewed records of hazard events that have occurred in the county since 2008, relying primarily on the Spatial Hazard Events and Losses Database for the United States (SHELDUS), compiled by the University of South Carolina’s Hazards and Vulnerability Research Institute and data from the National Oceanic and Atmospheric Administration’s (NOAA) National Climatic Data Center (NCDC) Storm Events Database. A summary of the findings for significant hazard occurrences is provided below in Table 4. The PDM Planning Team also identified potential hazards by observing development patterns, interviews from towns and townships, public meetings, PDM work sessions, previous disaster declarations and research of the history of hazard occurrences located within the County.

Table 4.1: Significant Hazard Occurrences

| Type of Hazard | # of Occurrences Since 2008 | Source |
| --- | --- | --- |
| Drought | 9 | NOAA & U of Neb-Lincoln |
| Wildfire/Forest Fire | 134 | NOAA & State Fire Marshall's Office |
| Flood | 7 | NOAA |
| Hail | 60 | NOAA & SHELDUS |
| Lightning | 0 | NOAA |
| Tornado | 8 | NOAA & SHELDUS |
| Temperature Extremes | 25 | NOAA |
| Winter Storms | 56 | NOAA |
| Thunderstorm and High Wind | 42 | NOAA & SHELDUS |

Hazards were analyzed in terms of the hazard’s probability of occurrence in the county. Representatives from each participating jurisdiction and the PDM Planning Team were asked to complete worksheets that categorized hazards by the likelihood of occurrence for either their specific geographical location, or for county-wide risks.

Every possible hazard or disaster was evaluated and placed into one of three separate columns depending on the likelihood of the disaster occurring in Clark County. Hazards that occur at least once a year or more were placed in the High Probability column; hazards that may have occurred in the past or could occur in the future but do not occur on a yearly basis were placed in the low probability column; and hazards or disasters that have never occurred in the area before and are unlikely to occur in the PDM jurisdiction any time in the future were placed in the Unlikely to Occur column.

Due to the topographical features of the County and the nature of the natural hazards that affect the geographical area covered by this PDM, most areas of the county have similar likelihood of being affected by the natural hazards identified. Only the natural hazards from the High Probability and Low Probability Columns will be further evaluated throughout this plan, with an emphasis on the High Probability hazards. All hazards in the Unlikely to Occur column will not be further evaluated in the plan. Table 4.2 is an adjusted list of hazards produced from the FEMA worksheets completed by each participating jurisdiction and the PDM Planning Team.

Table 4.2: Hazards Categorized by Likelihood of Occurrence

| High Probability |  | Low Probability |  | Unlikely to Occur |  |
| --- | --- | --- | --- | --- | --- |
| Extreme Cold | Flood | Extreme Heat | Ice Jam | Landslide | Dam Failure |
| Freezing Rain/Sleet/Ice | Hail | Tornado | Urban Fire | Earthquake | Subsidence |
| Heavy Rain | Heavy Snow |  |  |  |  |
| Lightning | Rapid Snow Melt |  |  |  |  |
| Strong Winds | Thunderstorm |  |  |  |  |
| Wild Fire | Utility Interruption |  |  |  |  |

TYPES OF NATURAL HAZARDS IN THE PDM JURISDICTION AREA

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B1.

Blizzards are a snow storm that lasts at least three hours with sustained wind speeds of thirty-five miles per hour (mph) or greater, visibility of less than one-quarter mile, temperatures lower than 20°F and white out conditions. Snow accumulations vary, but another contributing factor is loose snow existing on the ground which can get whipped up and aggravate the white out conditions. When such conditions arise, blizzard warnings or severe blizzard warnings are issued. Severe blizzard conditions exist when winds obtain speeds of at least forty-five mph plus a great density of falling or blowing snow and a temperature of 10°F or lower.

Drought is an extended period of months or years when a region notes a deficiency in its water supply. Generally, this occurs when a region receives consistently below average precipitation. It can have a substantial impact on the ecosystem and agriculture of the affected region. Although droughts can persist for several years, even a short, intense drought can cause significant damage and harm the local economy. This global phenomenon has a widespread impact on agriculture.

Dam Failure Dams function to serve the needs of flood control, recreation, and water management. During a flood, a dam’s ability to serve as a control agent may be challenged. An excessive amount of water may result in a dam breach, simply an overflowing. Dams that are old or unstable, dams that receive extreme amounts of water, or dams that get debris pile-up behind their face may result in dam failure, a cracking and/or breaking. The County has six dams, with all of the dams having a low potential to endanger lives and damage property.

Earthquakes are a sudden rapid shaking of the earth caused by the shifting of rock beneath the earth's surface. Earthquakes can cause buildings and bridges to collapse, disrupt gas, electric and phone lines, and often cause landslides, flash floods, fires, avalanches, and tsunamis. Larger earthquakes usually begin with slight tremors but rapidly take the form of one or more violent shocks and are followed by vibrations of gradually diminishing force called aftershocks. The underground point of origin of an earthquake is called its focus; the point on the surface directly above the focus is the epicenter.

Extreme Cold What constitutes extreme cold and its effects can vary across different areas of the country. In regions relatively unaccustomed to winter weather, near freezing temperatures are considered “extreme cold,” however, Eastern South Dakota is prone to much more extreme temperatures than other areas in the country. Temperatures typically range between zero degrees Fahrenheit and 100 degrees Fahrenheit, so extreme cold could be defined in the Clark County PDM jurisdiction area as temperatures below zero.

Extreme Heat, also known as a Heat Wave, is a prolonged period of excessively hot weather, which may be accompanied by high humidity. There is no universal definition of a heat wave; the term is relative to the usual weather in the area. Temperatures in the County have a very wide range typically between 0 to 100 degrees Fahrenheit, therefore anything outside those ranges could be considered extreme. The term is applied both to routine weather variations and to extraordinary spells of heat which may occur only once a century.

Flooding is an overflow of water that submerges land, producing measurable property damage or forcing evacuation of people and vital resources. Floods can develop slowly as rivers swell during an extended period of rain, or during a warming trend following a heavy snow. Even a very small stream or dry creek bed can overflow and create flooding. Two different types of flooding hazards are present within the County.

- Inundation flooding occurs most often in the spring. The greatest risks are realized typically during a rapid snowmelt, before ice is completely off all of the rivers.

- Flash flooding is more typically realized during the summer months. This flooding is primarily localized, though enough rain can be produced to cause inundation flooding. Heavy, slow moving thunderstorms often produce large amounts of rain. The threat of flooding would be increased during times of high soil moisture.

Freezing Rain/Ice occurs when temperatures drop below thirty degrees Fahrenheit and rain starts to fall. Freezing rain coats objects with ice causing dangerous conditions like slippery surfaces, platforms, sidewalks, roads, and highways. Sometimes ice is unnoticeable and is then referred to as black ice. Black ice creates dangerous conditions, especially for traffic. Additionally, a quarter inch of frozen rain can significantly damage trees, electrical wires, weak structures, and other objects due to the additional weight bearing down on them.

Hail is formed through rising currents of air in a storm. These currents carry water droplets to a height at which they freeze and subsequently fall to earth as round ice particles. Hailstones usually consist mostly of water ice and measure between 5 and 150 millimeters in diameter, with the larger stones coming from severe and dangerous thunderstorms.

Heavy Rain is defined as precipitation falling with intensity in excess of 0.30 inches (0.762 cm) per hour. Short periods of intense rainfall can cause flash flooding while longer periods of widespread heavy rain can cause rivers to overflow.

Ice Jams occur when warm temperatures and heavy rain cause snow to melt rapidly. Snow melt combined with heavy rains can cause frozen rivers to swell, which breaks the ice layer on top of the river. The ice layer often breaks into large chunks, which float downstream and often pile up near narrow passages and other obstructions, such as bridges and dams.

Landslide is a geological phenomenon which includes a wide range of ground movement, such as rock falls, deep failure of slopes and shallow debris flows, which can occur in offshore, coastal and onshore environments. Although the action of gravity is the primary driving force for a landslide to occur, there are other contributing factors build up specific sub-surface conditions that make the area/slope prone to failure, whereas the actual landslide often requires a trigger before being released.

Lightning results from a buildup of electrical charges that happens during the formation of a thunderstorm. The rapidly rising air within the cloud, combined with precipitation movement within the cloud, results in these charges. Giant sparks of electricity occur between the positive and negative charges both within the atmosphere and between the cloud and the ground. When the potential between the positive and negative charges becomes too great, there is a discharge of electricity, known as lightning. Lightning bolts reach temperatures near 50,000˚ F in a split second. The rapid heating and expansion, and cooling of air near the lightning bolt causes thunder.

Severe Winter Storms deposit four or more inches of snow in a twelve-hour period or six inches of snow during a twenty-four-hour period. Such storms are generally classified into four categories with some taking the characteristics of several categories during distinct phases of the storm. These categories include: freezing rain, sleet, snow, and blizzard. Generally winter storms can range from moderate snow to blizzard conditions and can occur between October and April. The months of May, June, July, August, and September could possibly see snow, though the chances of a storm are very minimal. Like summer storms, winter storms are considered a weather event not a natural hazard, and thus will not be evaluated as a natural hazard throughout this PDM.

Sleet does not generally cling to objects like freezing rain, but it does make the ground very slippery. This also increases the number of traffic accidents and personal injuries due to falls. Sleet can severely slow down operations within a community. Not only is there a danger of slipping, but with wind, sleet pellets become powerful projectiles that may damage structures, vehicles, or other objects.

Snow is a common occurrence throughout the County during the months from October to April. Average annual snowfall for the county can range up to thirty-four inches. Accumulations in dry years can be as little as five to ten inches, while wet years can see yearly totals up to eighty inches. Snow is a major contributing factor to flooding, primarily during the spring months of melting.

Strong winds are usually defined as winds over forty miles per hour, are not uncommon in the area. Winds over fifty miles per hour can be expected twice each summer. Strong winds can cause destruction of property and create safety hazards resulting from flying debris. Strong winds also include severe localized wind blasting down from thunderstorms. These downward blasts of air are categorized as either microburst or macroburst depending on the amount geographical area they cover. Microbursts cover an area less than 2.5 miles in diameter and macrobursts cover an area greater than 2.5 miles in diameter.

Subsidence is defined as the motion of a surface as it shifts downward relative to a datum. The opposite of subsidence is uplift, which results in an increase in elevation. There are several types of subsidence such as dissolution of limestone, mining-induced, faulting induced, isocratic rebound, extraction of natural gas, ground-water related, and seasonal effects.

Summer Storms are generally defined as atmospheric hazards resulting from changes in temperature and air pressure which cause thunderstorms that may cause hail, lightning, strong winds, and tornados. Summer storms are considered a weather event rather than a natural hazard; therefore, summer storms are not evaluated as a natural hazard throughout this PDM.

Thunderstorms are formed when moisture, rapidly rising warm air, and a lifting mechanism such as clashing warm and cold air masses combine. The three most dangerous items associated with thunderstorms are hail, lightning, and strong winds.

Tornados are violent windstorms that may occur singularly or in multiples as a result of severe thunderstorms. They develop when cool air overrides warm air, causing the warm air to rapidly rise. Many of these resulting vortices stay in the atmosphere, though touchdown can occur. The Fujita Tornado Damage Scale categorizes tornadoes based on their wind speed:

F0=winds less than 73 m/hF5=winds 261-318 m/h

F1=winds 73-112 m/hF6=winds greater than 318 m/h

F2=winds 113-157 m/h

F3=winds 158-206 m/h

F4=winds 207-260 m/h

Wildfires are uncontrolled conflagrations that spread freely through the environment. Other names such as brush fire, bushfire, forest fire, grass fire, hill fire, peat fire, vegetation fire, and wild fire may be used to describe the same phenomenon. A wildfire differs from the other fires by its extensive size; the speed at which it can spread out from its original source; its ability to change direction unexpectedly; and to jump gaps, such as roads, rivers and fire breaks.

Fires start when an ignition source is brought into contact with a combustible material that is subjected to enough heat and has an adequate supply of oxygen from the ambient air. Ignition may be triggered by natural sources such as a lightning strike or may be attributed to a human source such as “discarded cigarettes, sparks from equipment, and arched power lines.

Climate Change is the long-term change in the earth’s climate, especially a change due to an increase in the average atmospheric temperature. In particular, a change apparent from the mid to late 20th century onwards and attributed largely to the increased levels of atmospheric carbon dioxide produced by the use of fossil fuels. Rising temperatures will lead to more climate and weather hazards of greater intensity such as flooding, droughts, severe storms and winter storms. Many scientists consider climate change a global phenomenon.

HAZARD PROFILE

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B1.

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B2.

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B3.

It should be stated that most of the hazards identified in the previous section have the potential of occurring anywhere in the County. A brief section about the history of each hazard’s occurrence in the county is provided. Table 4.3 below shows all of the Presidential Disaster Declarations that have involved the county. Information on previous occurrences – the location, the extent (i.e., magnitude or severity) of each hazard, and probability of future events (i.e., chance or occurrence) are listed individually by the type of hazard in the following tables.

Table 4.3: Presidential Disaster Declarations in South Dakota Including Clark County

| Date | Disaster Dec # | Type | Total Damage | Public Assistance Cost |
| --- | --- | --- | --- | --- |
| 07/19/1993 | 999 | Tornadoes | $53,068,748 |  |
| 06/21/1994 | 1031 | Flooding | $8,187,938 |  |
| 05/26/1995 | 1052 | Flooding | $35,649,349 |  |
| 01/05/1996 | 1075 | Ice Storm | $13,085,649 |  |
| 01/10/1997 | 1156 | Blizzard | $19,455,263 |  |
| 04/07/1997 | 1173 | Flooding | $87,069,429 |  |
| 05/17/2001 | 1375 | Sever Storm | $5,097,818 |  |
| 10/20/2005 | 1620 | Winter Storm |  | $24,647,039 |
| 05/02/2007 | 1702 | Tornadoes and Flooding |  | $6,226,611 |
| 05/13/2010 | 1915 | Flooding |  | $21,498,619 |
| 05/13/2011 | 1984 | Flooding |  | $52,090,678 |
| 02/01/2017 | 4298 | Winter Storm |  | $9,632,647 |

Source: https://www.fema.gov/disasters

While the PDM Planning Team reviewed all hazard occurrences that have been reported in the last 60 years, the list for some of the hazards was extremely long. The information provided in the tables is not a complete history report, but rather an overview of the hazard events which have occurred over the last ten years. The PDM Planning Team felt the hazard trend for the last ten years could be summarized in this section and decided to include any new occurrence that have taken place since the 2013 PDM was drafted and approved.

DAM FAILURE

Dam breach or failure is of lesser concern for the citizens of the County than flooding. Clark County has a number of structures which control or regulate flow from one water body to another. South Dakota Department of Environment and Natural Resources identifies five dams in the County (Table 4.4 listed below). None of the dams are listed as vulnerable to failure.

4.4 Dam Locations in Clark County

| Ownership Type | Location | Water Body |
| --- | --- | --- |
| Private | NESW SE 16 T114N R59W | Timber Creek |
| Private | SENE SEC20 T115N R56W | Foster Creek - Tributary |
| State of South Dakota | SESW SEC 20 T116N R59W | Foster Creek - Tributary |
| State of South Dakota | SENW SEC16 T115N R59W | Foster Creek - Tributary |
| Private | SSE SEC3 T114N R59W | Shue Creek |

Source: SD DENR

DROUGHT AND WILDFIRE

South Dakota's climate is characterized by cold winters and warm to hot summers. There is usually light moisture in the winter and marginal to adequate moisture for the growing season for crops in the eastern portion of the state. Semi-arid conditions prevail in the western portion. This combination of hot summers and limited precipitation in a semi-arid climatic region places South Dakota with a potential position of suffering a drought in any given year. The climatic conditions are such that a small departure in the normal precipitation during the hot peak growing period of July and August could produce a partial or total crop failure.

The fact South Dakota's economy is closely tied to agriculture only magnifies the potential loss which could be suffered by the state's economy during drought conditions. Roughly every 50 years a significant drought is experienced within the county, while many less severe droughts can occur at times every three years. Table 4.5 identifies the ten-year drought history for the County.

Table 4.5:  Clark County Ten Year Drought History

| Location | Date Start | Date End | Type |
| --- | --- | --- | --- |
| Clark County | 09/06/2011 | 05/01/2012 | Moderate |
| Clark County | 07/03/2012 | 05/14/2013 | Moderate to Severe |
| Clark County | 08/27/2013 | 10/15/2013 | Moderate to Severe |
| Clark County | 12/02/2014 | 06/09/2015 | Moderate |
| Clark County | 04/12/2016 | 01/26/2016 | Moderate |
| Clark County | 06/06/2017 | 06/13/2017 | Moderate |
| Clark County | 07/11/2017 | 08/08/2017 | Moderate |
| Clark County | 02/06/2018 | 03/06/2018 | Moderate |
| Clark County | 06/05/2018 | 07/24/2018 | Moderate to Severe |

Source: https://droughtmonitor.unl.edu/Data/DataTables.aspx

A strong possibility exists for simultaneous emergencies during droughts. Wildfires are the most common. While researching the hazard occurrences that have taken place in the County, it became evident that the information found on the NOAA and SHELDUS websites was incomplete. Therefore, other sources were contacted whenever possible. Specifically, NOAA had zero occurrences listed for wildfires in the County, but the State Fire Marshal’s Office (SFMO) was contacted to verify that information. The SFMO information provided is derived from the reports submitted by the local fire departments who respond to the fires. Representatives from the SFMO explained that since many of the fire departments in the County are Volunteer Fire Departments many times wildfires are extinguished, and reports are never filed with the SFMO. Thus, the information provided by the SFMO is not entirely complete either. For the purpose of this PDM we have used the numbers provided by the SFMO as a point of reference in determining the likelihood of a wildfire hazard occurrence within the jurisdiction. The information provided by the SFMO identifies 37 structure fire responses, 31 vehicle fire responses, and 66 outside fire responses reported from 2008 to 2017. The cause of the outside fires is not listed, so it is not known for certain whether all or some of these fires resulted due to a natural hazard occurrence or as a result of human behavior. Additionally, The SFMO provided information about the number of injuries and fatalities reported as a result of these fires. According to the information provided, zero civilian and zero firefighter injuries were reported from 2008 to 2017. During the same time period, zero civilian fatalities and zero firefighter fatalities were also reported.

Table 4.6 identifies the number of fire department responses to structural, vehicle and outside fires that have been experienced within the county. It should be noted that the number of responses does not necessarily mean that there were 66 outside (wildfire) fires as some fires required multiple departments to respond. The 2013 PDM plan did not list or identify the history of wildfire occurrences.

Table 4.6: Clark County Structural, Vehicle and Outside (Wildfire) Department Responses

| Year | Structural Fires | Vehicle Fires | Outside Fires |
| --- | --- | --- | --- |
| 2008 | 8 | 7 | 4 |
| 2009 | 9 | 5 | 9 |
| 2010 | 6 | 3 | 6 |
| 2011 | 2 | 1 | 2 |
| 2012 | 0 | 0 | 5 |
| 2013 | 2 | 2 | 3 |
| 2014 | 3 | 2 | 6 |
| 2015 | 1 | 2 | 7 |
| 2016 | 3 | 2 | 17 |
| 2017 | 3 | 7 | 7 |
| Total | 37 | 31 | 66 |

SOURCE: South Dakota State Fire Marshall Office

EARTHQUAKES

An earthquake is the result of a sudden release of energy due to an adjustment in the earth’s crust. This adjustment causes the ground to tremble and produces vibrations that radiate out from the focus of the quake. In South Dakota, the most likely causes for earthquakes would be from plate movements along faults and isocratic (glacial) rebound. Severe enough earthquakes can cause property damages and injuries or loss of lives. In 2005, a 3.1 magnitude earthquake was registered in neighboring Miner County. No earthquake activity has been recorded in Clark County.

FLOOD

Flooding is a temporary overflow of water onto lands not normally covered by water producing measurable property damage or forcing evacuation of people and resources. Floods can result in injuries and even loss of life when quickly moving water is involved. Six inches of moving water is enough to sweep a vehicle off a road. Disruption of communication, transportation, electric service, and community services, along with contamination of water supplies and transportation accidents are very possible. Table 4.7 is a ten-year flood history in the County from 2007 to 2017.

Table 4.7:  Clark County Ten-year Flood History

| Location or County | Type | Date | Time | Property Damage |
| --- | --- | --- | --- | --- |
| Raymond | Flash Flood | 07/14/2009 | 2:00 a.m. | 0 K |
| Crocker | Flood | 03/15/2010 | 8:00 a.m. | 0 K |
| Crocker | Flood | 03/15/2011 | 8:00 a.m. | 0 K |
| Raymond | Flash Flood | 07/07/2010 | 3:00 a.m. | 0 K |
| Raymond | Flash Flood | 09/15/2010. | 5:26 p.m. | 0 K |
| Crocker | Flood | 04/01/2011 | 12:00 a.m. | 0 K |
| Carpenter | Flash Flood | 08/15/2014 | 1:30 a.m. | 0 K |

SOURCE: https://www.ncdc.noaa.gov/stormevents/

HAIL

Table 4.8 indicates hail occurrences by location throughout the county. However, the information provided by the NOAA website is incomplete due to inconsistent reporting after such hazards occur. Obviously, with such a high number of occurrences it is reasonable to expect that at least some property or crop damage was sustained in the communities during some of the occurrences, even though the damage may not have been reported or recorded. It is possible that such damage was not reported because it was believed to be insignificant at the time, or because those responsible for reporting such information did not report to the proper agencies.

Table 4.8: Clark County Ten-year Hail History

| Location or County | Date | Time | Magnitude |
| --- | --- | --- | --- |
| Carpenter | 06/11/2008 | 4:25 a.m. | 0.75 in. |
| Willow Clark | 06/12/2008 | 3:16 p.m. | 1.00 in. |
| Willow Lake | 09/28/2008 | 3:50 p.m. | 0.88 in. |
| Raymond | 05/31/2009 | 4:20 p.m. | 1.00 in. |
| Clark | 05/31/2009 | 4:35 p.m. | 1.00 in. |
| Willow Lake | 05/31/2009 | 5:10 p.m. | 1.00 in. |
| Raymond | 06/18/2009 | 6:30 p.m. | 1.00 in. |
| Crocker | 06/24/2009 | 1:01 p.m. | 0.88 in. |
| Bradley | 06/24/2009 | 8:43 p.m. | 0.75 in. |
| Clark | 07/07/2009 | 1:53 p.m. | 0.88 in. |
| Willow Lake | 07/07/2009 | 1:55 p.m. | 0.88 in. |
| Naples | 07/07/2009 | 2:12 p.m. | 1.00 in. |
| Carpenter | 07/07/2009 | 2:15 p.m. | 0.88 in. |
| Willow Lake | 07/07/2009 | 2:17 p.m. | 1.00 in. |
| Willow Lake | 07/07/2009 | 3:57 p.m. | 0.88 in. |
| Clark County Airport | 07/09/2009 | 00:31 a.m. | 1.00 in. |
| Garden City | 07/09/2009 | 01:00 a.m. | 1:00 in. |
| Raymond | 07/06/2010 | 7:18 p.m. | 0.88 in. |
| Willow Lake | 07/06/2010 | 8:22 p.m. | 1.00 in. |
| Naples | 07/06/2010 | 8:40 p.m. | 0.88 in. |
| Crocker | 07/17/2010 | 3:51 p.m. | 2.75 in. |
| Crocker | 07/17/2010 | 4:15 p.m. | 1.75 in. |
| Crocker | 07/17/2010 | 4:20 p.m. | 1.75 in. |
| Clark | 07/17/2010 | 4:30 p.m. | 2.00 in. |
| Clark | 07/17/2010 | 4:34 p.m. | 1.75 in. |
| Clark | 07/17/2010 | 4:35 p.m. | 2.75 in. |
| Garden City | 07/17/2010 | 4:37 p.m. | 1.50 in. |
| Location or County | Date | Time | Magnitude |
| Elrod | 07/17/2010 | 4:38 p.m. | 2.50 in. |
| Naples | 07/17/2010 | 4:56 p.m. | 1.00 in. |
| Naples | 07/17/2010 | 5:01 p.m. | 1.75 in. |
| Garden City | 09/01/2010 | 10:55 p.m. | 1.00 in. |
| Bradley | 05/21/2011 | 5:30 p.m. | 0.75 in. |
| Raymond | 05/30/2011 | 2:15 a.m. | 1.00 in. |
| Carpenter | 06/13/2011 | 4:55 p.m. | 1.75 in. |
| Crocker | 06/26/2011 | 2.01 a.m. | 1.75 in. |
| Clark | 07/01/2011 | 12.40 p.m. | 1.50 in. |
| Clark | 07/01/2011 | 12:46 p.m. | 0.75 in. |
| Bradley | 05/02/2012 | 6:35 p.m. | 1.00 in. |
| Bradley | 05/02/2012 | 6:45 p.m. | 0.88 in. |
| Willow Lake | 05/05/2012 | 7:00 p.m. | 1.00 in. |
| Clark | 06/01/2012 | 7:02 p.m. | 1.00 in. |
| Raymond | 09/18/2013 | 8:55 p.m. | 1.25 in. |
| Clark | 09/18/2013 | 10:30 p.m. | 1.00 in. |
| Willow Lake | 07/24/2014 | 9:23 a.m. | 1.00 in. |
| Bradley | 07/24/2014 | 12:25 p.m. | 1.00 in. |
| Willow Lake | 06/06/2015 | 5:30 p.m. | 0.75 in. |
| Willow Lake | 06/06/2015 | 5:45 p.m. | 1.00 in. |
| Willow Lake | 06/09/2015 | 4:24 p.m. | 1.00 in. |
| Bradley | 07/17/2015 | 7:26 p.m. | 1.00 in. |
| Naples | 08/06/2015 | 2:52 p.m. | 1.00 in |
| Raymond | 07/16/2016 | 6:40 p.m. | 1.00 in. |
| Raymond | 07/16/2016 | 6:45 p.m. | 1.00 in. |
| Raymond | 07/16/2016 | 6;50 p.m. | 1.75 in. |
| Clark | 07/16/2016 | 7:19 p.m. | 1.75 in. |
| Clark | 07/16/2016 | 7:20 p.m. | 2.50 in. |
| Location or County | Date | Time | Magnitude |
| Garden City | 06/11/2017 | 3:38 a.m. | 1.00 in. |
| Carpenter | 06/22/2017 | 2:40 a.m. | 1.00 in. |
| Elrod | 07/17/2017 | 4:03 p.m. | 0.88 in. |
| Naples | 08/13/2017 | 10:33 a.m. | 1.75 in. |
| Bradley | 05/08/2018 | 5:15 p.m. | 1.00 in. |

SOURCE: https://www.ncdc.noaa.gov/stormevents/

LIGHTNING

The extent or severity of lightning can range from significant to insignificant depending on where it strikes and what structures are hit. Water towers, cell phone towers, power lines, trees, and common buildings and structures all have the possibility of being struck by lightning. People who leave shelter during thunderstorms to watch or follow lightning also have the possibility of being struck by lightning. According to the NCDC database, there have been no reported lightning events in Clark County for the past ten years. However, the possibility exists that the information is incomplete. It is also important to note that while no damage was reported, lightning strikes are very common in all South Dakota counties.

TORNADO

The annual risk for intense summer storms is very high. The entire County is susceptible to summer storms. Warning time for summer storms is normally several hours, sufficient for relocation and evacuation if necessary. Between the years of 2007 and 2017, the County confirmed eight tornadoes/funnels. However, tornadoes may occur with little or no warning. Table 4.9 includes the tornado history in the County over the course of the past ten years.

Table 4.9: Clark County Ten-year Tornado History

| Location | Date | Time | Type | Magnitude | Injuries | Property Damage |
| --- | --- | --- | --- | --- | --- | --- |
| Raymond | 06/01/2012 | 6:59 p.m. | Tornado | 0 | 0 | 0 |
| Willow Lake | 06/01/2012 | 7:48 p.m. | Tornado | 0 | 0 | 0 |
| Willow Lake | 06/01/2012 | 8:14 p.m. | Tornado | 0 | 0 | 0 |
| Carpenter | 06/21/2013 | 1:55 p.m. | Tornado | 0 | 0 | 0 |
| Carpenter | 06/21/2013 | 2:08 p.m. | Tornado | 0 | 0 | 0 |
| Clark | 07/16/2016 | 7:23 p.m. | Tornado | 0 | 0 | 0 |
| Location | Date | Time | Type | Magnitude | Injuries | Property Damage |
| Clark | 09/19/2017 | 7;55 p.m. | Tornado | 0 | 0 | 0 |
| Bradley | 09/19/2017 | 8:26 p.m. | Tornado | 0 | 0 | 0 |

SOURCE: https://www.ncdc.noaa.gov/stormevents/

Clark County’s considered to be in an F3 area, as is the rest of South Dakota. Wind speeds can get up to 206 mph at times during an F3 tornado. Tornadoes in South Dakota can reach F5, with wind speeds gusting up to 318 mph. Despite these facts, tornadoes are much less likely to occur in this area than other types of severe summer weather.

Each year, many storms and a few tornadoes affect the county. Summer storms in the County usually produce a wide range of damage making damage estimates very difficult. A complete listing of all summer storms having occurred within the county is not possible due to inaccurate reporting. The NWS reports online were the primary source for this information.

EXTREME TEMPERATURES

Extreme temperatures in the County are common occurrences. It is expected that at least two times each year there will be extreme heat or extreme cold in the area. The following information was found on the NOAA website. It is possible that people in the area have adapted to this type of extreme temperatures and thus such weather events are not reported as often as they occur. It is also possible that the information has only in recent years been tracked or reported. Table 4.10 identifies dates and times of the temperature extremes.

Table 4.10: Clark County 10-year History of Extreme Temperatures

| Location | Date | Time | Type |
| --- | --- | --- | --- |
| Clark County | 01/29/2008 | 8:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 02/10/2008 | 5:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 02/19/2008 | 8:00 p.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/15/2008 | 1:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/21/2008 | 1:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/13/2009 | 9:00 p.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/07/2010 | 10:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 02/02/2011 | 2:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 02/08/2011 | 4:00 a.m. | Extreme Cold/ Wind Chill |
| Location | Date | Time | Type |
| Clark County | 07/16/2011 | 12:00 p.m. | Excessive Heat |
| Clark County | 01/20/2013 | 10:00 p.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/31/2013 | 2:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/07/2013 | 5:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/23/2013 | 1:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/29/2013 | 7:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/05/2014 | 4:00 p.m. | Extreme Cold/ Wind Chill |
| Clark County | 03/02/2014 | 7:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/16/2016 | 10:55 p.m. | Extreme Cold/ Wind Chill |
| Clark County | 07/20/2016 | 12:00 p.m. | Excessive Heat |
| Clark County | 12/18/2016 | 2:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/26/2017 | 7:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 12/30/2017 | 6:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/01/2018 | 00:00 a.m. | Extreme Cold/ Wind Chill |
| Clark County | 01/15/2018 | 7:30 a.m. | Extreme Cold/ Wind Chill |

SOURCE: https://www.ncdc.noaa.gov/stormevents

THUNDERSTORMS/HIGH WIND

Thunderstorms and high wind occurrences in the County are also very common. According to the NOAA database, the County experienced forty-two wind events from 2007-2017. Table 4.11 denotes the extent and severity of such hazards occurring in the last ten years. The County continues to educate residents of the dangers of such storms through public service announcements and other printed media.

Table 4.11:  Clark County 10-year History for Thunderstorms

| Location | Date | Time | Type | Mag (kts) |
| --- | --- | --- | --- | --- |
| Naples | 08/08/2007 | 6:15 p.m. | Thunderstorm Wind | 52 |
| Elrod | 07/16/2008 | 10:35 p.m. | Thunderstorm Wind | 56 |
| Location | Date | Time | Type | Mag (kts) |
| Garden City | 07/28/2008 | 10:15 p.m. | Thunderstorm Wind | 61 |
| Elrod | 07/07/2009 | 2:15 p.m. | Thunderstorm Wind | 52 |
| Raymond | 05/22/2010 | 10:40 p.m. | Thunderstorm Wind | 61 |
| Carpenter | 06/22/2010 | 11:40 p.m. | Thunderstorm Wind | 52 |
| Raymond | 07/06/2010 | 7:00 p.m. | Thunderstorm Wind | 52 |
| Carpenter | 07/06/2010 | 7:50 p.m. | Thunderstorm Wind | 52 |
| Bradley | 07/17/2010 | 4:30 p.m. | Thunderstorm Wind | 56 |
| Elrod | 07/17/2010 | 7:60 p.m. | Thunderstorm Wind | 61 |
| Raymond | 07/23/2010 | 7:00 p.m. | Thunderstorm Wind | 52 |
| Crocker | 08/30/2010 | 4:45 p.m. | Thunderstorm Wind | 61 |
| Clark | 08/30/2010 | 5:00 p.m. | Thunderstorm Wind | 61 |
| Clark County | 10/26/2010 | 2:00 p.m. | High Winds | 35 |
| Bradley | 06/19/2012 | 2:00 a.m. | Thunderstorm Wind | 52 |
| Raymond | 08/03/2012 | 5:15 p.m. | Thunderstorm Wind | 52 |
| Garden City | 08/03/2012 | 5:36 p.m. | Thunderstorm Wind | 52 |
| Clark County Airport | 05/19/2013 | 00.55 a.m. | Thunderstorm Wind | 69 |
| Carpenter | 06/21/2013 | 1:54 p.m. | Thunderstorm Wind | 66 |
| Vienna | 06/21/2013 | 2:10 p.m. | Thunderstorm Wind | 70 |
| Elrod | 06/21/2013 | 2:40 p.m. | Thunderstorm Wind | 52 |
| Elrod | 06/21/2013 | 3:00 p.m. | Thunderstorm Wind | 52 |
| Willow Lake | 08/28/2013 | 6:35 a.m. | Thunderstorm Wind | 61 |
| Raymond | 06/19/2014 | 3:40 a.m. | Thunderstorm Wind | 52 |
| Location | Date | Time | Type | Mag (kts) |
| Willow Lake | 06/09/2015 | 4:13 p.m. | Thunderstorm Wind | 56 |
| Bradley | 07/17/2015 | 7:15 p.m. | Thunderstorm Wind | 61 |
| Raymond | 07/25/2015 | 6:35 p.m. | Thunderstorm Wind | 52 |
| Carpenter | 07/25/2015 | 6:50 p.m. | Thunderstorm Wind | 52 |
| Clark County | 10/12/2015 | 5:50 a.m. | High Winds | 55 |
| Clark County | 11/12/2015 | 12:10 p.m. | High Winds | 50 |
| Clark County | 11/18/2015 | 8:10 p.m. | High Winds | 58 |
| Clark County | 02/07/2016 | 4:00 p.m. | High Winds | 35 |
| Clark County | 03/07/2017 | 2:00 p.m. | High Winds | 35 |
| Willow Lake | 05/28/2017 | 4:33 p.m. | Thunderstorm Wind | 52 |
| Clark | 06/11/2017 | 3:40 a.m. | Thunderstorm Wind | 61 |
| Clark | 06/13/2017 | 5:58 p.m. | Thunderstorm Wind | 70 |
| Clark | 06/13/2017 | 5:58 p.m. | Thunderstorm Wind | 80 |
| Elrod | 06/13/2017 | 6:05 p.m. | Thunderstorm Wind | 56 |
| Carpenter | 07/17/2017 | 5:15 p.m. | Thunderstorm Wind | 52 |
| Clark County | 11/29/2017 | 12:00 p.m. | High Winds | 50 |
| Elrod | 06/06/2018 | 00:33 a.m. | Thunderstorm Winds | 52 |

SOURCE: https://www.ncdc.noaa.gov/stormevents/

WINTER STORMS

Table 4.12 shows just how common snow and ice storms are in the County. While such storms would be considered extreme in many parts of the State, the consistent nature of such weather hazards are expected in this area. Thus, planning and response mechanisms for snow and ice storms are vital to the County and are routine procedures in the County due to the common nature of such storms. Winter storms in South Dakota are known to cover large geographical areas, often an entire county or multiple counties can be affected by a single storm. Due to the multiple occurrences of winter storms each year, an exhaustive compilation is not possible.

Table 4.12: Clark County 10-year history of Snow and Ice Storms

| Location | Date | Time | Type |
| --- | --- | --- | --- |
| Clark County | 02/28/2007 | 2:00 a.m. | Heavy Snow |
| Clark County | 02/23/2007 | 10:00 a.m. | Winter Storm |
| Clark County | 03/02/2007 | 9:15 a.m. | Blizzard |
| Clark County | 12/01/2007 | 5:00 a.m. | Heavy Snow |
| Clark County | 03/20/2008 | 2:00 p.m. | Heavy snow |
| Clark County | 03/26/2008 | 8:00 p.m. | Heavy Snow |
| Clark County | 03/31/2008 | 1:00 a.m. | Heavy Snow |
| Clark County | 04/10/2008 | 2:00 p.m. | Blizzard |
| Clark County | 04/25/2008 | 7:00 a.m. | Winter Storm |
| Clark County | 11/06/2008 | 4:00 p.m. | Blizzard |
| Clark County | 12/13/2008 | 7:00 p.m. | Blizzard |
| Clark County | 12/19/2008 | 11:00 p.m. | Blizzard |
| Clark County | 01/12/2009 | 2:00 a.m. | Blizzard |
| Clark County | 02/26/2009 | 3:00 a.m. | Winter Storm |
| Clark County | 12/23/2009 | 7:00 p.m. | Blizzard |
| Clark County | 01/06/2010 | 4:00 a.m. | Winter Storm |
| Clark County | 01/22/2010 | 2:00 p.m. | Winter Storm |
| Clark County | 01/25/2010 | 10:00 a.m. | Blizzard |
| Clark County | 12/11/2010 | 9:00 a.m. | Blizzard |
| Clark County | 12/30/2010 | 12:00 p.m. | Blizzard |
| Location | Date | Time | Type |
| Clark County | 12/31/2010 | 11:00 a.m. | Blizzard |
| Clark County | 01/01/2011 | 00:00 a.m. | Blizzard |
| Clark County | 02/20/2011 | 12:00 p.m. | Blizzard |
| Clark County | 03/11/2011 | 8:00 p.m. | Blizzard |
| Clark County | 03/22/2011 | 10:00 p.m. | Heavy Snow |
| Clark County | 02/28/2012 | 4:00 p.m. | Winter Storm |
| Clark County | 12/08/2012 | 3:00 p.m. | Winter Storm |
| Clark County | 12/09/2012 | 8:00 a.m. | Blizzard |
| Clark County | 02/10/2013 | 6:00 p.m. | Blizzard |
| Clark County | 02/18/2013 | 11:00 a.m. | Blizzard |
| Clark County | 03/08/2013 | 7:00 p.m. | Ice Storm |
| Clark County | 03/18/2013 | 4:00 a.m. | Blizzard |
| Clark County | 04/10/2013 | 8:00 p.m. | Winter Storm |
| Clark County | 01/14/2013 | 3:00 a.m. | Ice Storm |
| Clark County | 12/03/2013 | 11:00 a.m. | Winter Storm |
| Clark County | 01/16/2014 | 10:00 a.m. | Blizzard |
| Clark County | 01/18/2014 | 3:00 a.m. | Blizzard |
| Clark County | 01/22/2014 | 5:00 a.m. | Blizzard |
| Clark County | 01/25/2014 | 6:00 p.m. | Blizzard |
| Clark County | 03/31/2014 | 6:30 p.m. | Blizzard |
| Clark County | 11/09/2014 | 10:00 a.m. | Heavy Snow |
| Clark County | 01/08/2015 | 1:45 p.m. | Blizzard |
| Clark County | 03/03/2015 | 6:00 a.m. | Blizzard |
| Clark County | 11/30/2015 | 9:00 a.m. | Heavy Snow |
| Clark County | 12/01/2015 | 00:00 a.m. | Heavy Snow |
| Clark County | 02/13/2016 | 10:00 p.m. | Winter Storm |
| Clark County | 11/18/2016 | 7:00 a.m. | Blizzard |
| Clark County | 12/10/2016 | 11:00 a.m. | Heavy Snow |
| Clark County | 12/16/2016 | 11:00 a.m. | Heavy Snow |
| Location | Date | Time | Type |
| Clark County | 12/25/2016 | 12:00 p.m. | Ice Storm |
| Clark County | 12/26/2016 | 11:00 a.m. | Blizzard |
| Clark County | 03/12/2017 | 9:00 a.m. | Heavy Snow |
| Clark County | 12/04/2017 | 4:00 p.m. | Blizzard |
| Clark County | 03/05/2018 | 6:00 a.m. | Heavy Snow |
| Clark County | 04/08/2018 | 9:00 a.m. | Heavy Snow |
| Clark County | 04/13/2018 | 11:00 a.m. | Blizzard |

SOURCE: https://www.ncdc.noaa.gov/stormevents

Climate Change

Climate change is a global phenomenon. Human related activities are releasing increasing quantities of carbon dioxide and other heat trapping gases into the Earth’s atmosphere causing increases in temperatures worldwide. Dennis Todey, Extension State Climatologist, predicts increased precipitation in the northern Great Plains with more heavy precipitation events and flooding. Warmer temperatures will lengthen the growing season and increase the number of frost-free days. Total snow fall accumulations will decrease. Overall, climate change will increase the number and intensity of weather hazards in the region.

ASSESSING VULNERABILITY: OVERVIEW

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B1.

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B2.

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B3.

Hazards were also analyzed in terms of the level of the community or county’s vulnerability to the hazard. Vulnerability to the hazard is the susceptibility of life, property, and the environment to injury or damage if a hazard occurs. Representatives from each participating jurisdiction and the PDM Planning Team were asked to complete worksheets that rated their perception to vulnerability of hazards for either their specific geographical location, or for county-wide risks. A low vulnerability hazard is one that has very low damage potential to either life or property (minor damage to less than 5% of the jurisdiction). A “medium” vulnerability hazard is unlikely to threaten human life, although some people may be at risk, but may pose moderate damage potential (causing partial damage to 5% to 10% of the jurisdiction, on an irregular occurrence). A “high” vulnerability hazard may threaten human life, and more than ten percent of the jurisdiction may be at risk on a regular occurrence. Table 4.13 below is an overall summary of vulnerability by jurisdiction produced from the FEMA worksheets completed by each participating jurisdiction and PDM Planning Team.

Table 4.13: Overall Summary of Vulnerability by Jurisdiction

| Type of Disaster | Clark County | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Codington Clark Co-Op |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Dam Failure | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | L |
| Drought | H | L | L | N/A | L | L | L | H | M |
| Earthquake | N/A | L | N/A | N/A | N/A | N/A | N/A | L | N/A |
| Extreme Cold | H | M | H | M | H | H | H | M | H |
| Extreme Heat | H | M | H | M | H | L | H | M | H |
| Flood | L | L | M | L | L | M | M | L | M |
| Freezing Rain/Sleet/Ice | M | H | H | H | H | M | H | H | H |
| Hail | M | M | H | H | H | M | H | H | M |
| Heavy Rain | M | H | H | L | H | M | H | M | M |
| Heavy Snow | M | H | H | M | H | L | H | H | M |
| Ice Jam | N/A | N/A | N/A | L | N/A | L | N/A | L | L |
| Landslide | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |
| Lightning | L | L | H | L | M | L | M | L | L |
| Rapid Snow Melt | M | M | H | L | H | L | H | M | L |
| Strong Winds | M | H | H | M | H | M | H | H | M |
| Subsidence | N/A | L | L | N/A | N/A | N/A | N/A | N/A | N/A |
| Thunderstorm | M | L | H | L | M | M | M | H | M |
| Tornado | L | M | H | H | M | M | H | H | M |
| Urban Fire | L | L | H | L | M | L | M | L | L |
| Utility Interruption | L | H | H | M | M | L | M | L | M |
| Wild Fire | L | L | H | L | M | L | M | M | L |

The following paragraphs summarize the description of the jurisdiction’s vulnerability to each

hazard and the impact of each hazard on the jurisdiction.

Blizzards are characterized by high winds, blowing snow, cold temperatures, and low visibility.  Blizzards create conditions such as icy roads, closed roads, downed power lines and trees. The County’s population is especially vulnerable to these conditions because people tend to leave their homes to get to places such as work, school, and stores rather than staying inside. Traffic is one of the biggest hazards in the County during a blizzard because people often get stuck, stranded, and lost when driving their vehicles which usually prompts others such as family and or emergency responders to go out in the conditions to rescue them.

Drought can be defined as a period of prolonged lack of moisture. High temperatures, high winds, and low relative humidity all result from droughts and are caused by droughts. A decrease in the amount of precipitation can adversely affect stream flows and reservoirs, lakes, and groundwater levels. Crops and other vegetation are harmed when moisture is not present within the soil.

Earthquakes occur in the area but have not had a great enough magnitude or intensity in the past ten years to be reported. The magnitude and intensity of an earthquake is measured by the Richter scale and the Mercalli scale. An earthquake of noteworthy magnitude has not occurred in the county for decades, but it would be reasonable to expect that a large earthquake would have comparative impact on the County as it would anywhere else. The County does not have skyscrapers or very many tall buildings, but it also does not have codes in place that require homes or buildings to be retrofitted.

Extreme Cold temperatures often accompany a winter storm, so you may have to cope with power failures and icy roads. Whenever temperatures drop decidedly below normal and as wind speed increases, heat can leave your body more rapidly. These weather-related conditions may lead to serious health problems. Extreme cold is a dangerous situation that can bring on health emergencies in susceptible people, such as those without shelter or who are stranded, or who live in a home that is poorly insulated or without heat. Exposure is the biggest threat/vulnerability to human life; however, incidences of exposure are isolated and thus unlikely to happen in masses.

Extreme Heat Severe heat waves have caused catastrophic crop damage, thousands of deaths from hyperthermia, and widespread power failures due to increased use of air conditioning. Loss of power and crop damage is the largest vulnerabilities to the county during extreme heat. Both have an effect on quality of life, however, neither are detrimental to the existence of the population of the County.

Flooding can result in injuries and even loss of life when quickly moving water is involved. Six inches of moving water is enough to sweep a vehicle off a road. Disruption of communication, transportation, electric service, and community services, along with contamination of water supplies and transportation accidents are very possible.

Freezing Rain causes adverse conditions such as slippery surfaces and extra weight buildup on power lines, poles, trees, and structures. The additional weight can often cause weak structures to cave in and cause tree branches and power lines to break and fall. The County and the local jurisdictions within are susceptible to these conditions due to the types of structures and surfaces that exist in the county that cannot be protected from freezing rain. Traffic on the roads and highways tend to be the biggest hazard during freezing rain conditions because vehicles often slide off the road which prompts emergency responders and others to have to go out on rescue missions in the adverse conditions.

Hail causes damage to property such as crops, vehicles, windows, roofs, and structures. The County and its local jurisdictions are vulnerable to hail, like most other areas in the State due to the nature of the hazard. Mitigating for hail is difficult and is usually found in the form of insurance policies for structures, vehicles, and crops.

Heavy Rain causes damage to property such as homes and roads. Often when heavy rains occur in the County it may cause sewers to back-up in homes due to excess water entering the wastewater collection lines. The excess water sometimes has no place to go and thus basements fill up with water which results in damage to water heaters, furnaces, and damage to living quarters for people who live in basement apartments. Roads and bridges can be washed out, thus causing traffic hazards for travelers and commuters. Many times, the roads have to be closed causing rural traffic to have to take alternate routes which can sometimes be an additional five to ten miles out of the way. All areas of the County are vulnerable when heavy rains occur. Storm sewers are built for the typical storm and therefore do not accommodate for excessive or heavy rains.

Ice Jams cause damage to bridges, roads, and culverts due to water currents pushing large chunks of ice under or through small openings. Due to the topography of the County, there are very few rivers or creeks with flowing water. Therefore, vulnerability to ice jams is considered very low.

Landslides have a low chance of occurring in the County due to the relatively flat topography.

Lightning often strikes the tallest objects within the area. In towns trees and poles often receive the most strikes. In rural areas, shorter objects are more vulnerable to being struck. Electrical lines and poles are also vulnerable because of their height and charge. In addition, many streetlights function with sensors. Since thunderstorms occur primarily during hours of darkness, lightning strikes close to censored lights cause the lights to go out, causing a potential hazard for drivers. Flickering lights and short blackouts are not at all uncommon in the county.

One of lightning’s dangerous attributes includes the ability to cause fires. Since the entire county is vulnerable to lightning strikes and subsequent fires, these fires will be treated under the fire section of this PDM.

Most injuries from lightning occur near the end of thunderstorms. Individuals who sought shelter leave those areas prior to the entire completion of the thunderstorm. Believing it is safe to freely move around, concluding lightning strikes catch them off guard.

Severe Winter Storms have a high risk of occurrence. Heavy snow can immobilize transportation, down power lines and trees and cause the collapsing of weaker structures. Livestock and wildlife are also very vulnerable during periods of heavy snow. Most storms can be considered to have occurred countywide. Due to the multiple occurrences of winter storms each year, an exhaustive compilation is not possible.

Additionally, winter storms often result in some forms of utility mishaps. High voltage electric transmission/distribution lines run the length of the County. These lines are susceptible to breaking under freezing rain and icy conditions and severing during high blizzard winds. Any electrical complications bring associated risk of food spoilage, appliance burnout, loss of water, and potential harm for in-house life support users. Limited loss of power is not uncommon on an annual basis. A typical power interruption lasts from one to three hours. Most residents are prepared to deal with this type of inconvenience.

The greatest danger during winter weather is traveling. Many individuals venture out in inclement weather. Reasons include the necessity of getting to work, going to school, going out just to see how the weather is, and to rescue stranded persons.

Snow Drifts are caused by wind blowing snow and cold temperatures. These drifts can be small finger drifts on roadways causing cautionary driving, or 20 to 40-foot-high drifts that block entire highways, roads, and farmyards for several days.

As with any weather event, those dependent upon healthcare supplies and other essentials will also bear the brunt of highway closures and slowed transportation due to snow and ice. Emergency services will also be delayed during winter storms.

Snow removal policies and emergency response is at excellent performance and no projects will be considered in this area. Generators provide back-up power to many critical facilities within the municipalities and in rural areas. However, some of the critical facilities that could be utilized in disaster situations do not have backup generators. Also, some facilities have generators that only power a portion of operations.

Strong Winds can be detrimental to the area. Trees, poles, power lines, and weak structures are all susceptible and vulnerable to strong winds. When strong winds knock down trees, poles, power lines, and structures it creates additional traffic hazards for travelers and commuters.  Strong winds are a common occurrence in all parts of the County. The farming community tends to be vulnerable because many old farm sites have weak, dilapidated, or crumbling structures or structures such as grain bins which can easily be blown over. Another area of particular vulnerability would be those areas with dense tree growth where dead or decaying trees lose their stability and can be blown over or knocked down easily.

Thunderstorms cause lightening and sometimes large amounts of rain in a small timeframe. The entire county experiences thunderstorms on a regular basis and is only vulnerable when weather events outside the norm occur. Specific vulnerabilities are further identified in the paragraphs for “Lightening” and “Heavy Rains”.

Tornadoes present significant danger and occur most often in South Dakota during the months of May, June, and July. The greatest period of tornado activity (about 82 percent of occurrence) is from eleven a.m. to midnight. Within this time frame, most tornadoes occur between four p.m. and six p.m. The annual risk for intense summer storms is very high. Often associated with summer storms are utility problems. High voltage electrical transmission lines run the length of the County. These lines are susceptible to breaking during high winds and hail. Tall trees located near electrical lines can be broken in wind or by lightning strikes and land on electrical lines, severing connections. Any electrical complications bring associated risk of food spoilage, appliance burnout, loss of water, and potential harm to in-house life support dependents. Limited loss of power is common on an annual basis. Typical power interruptions last around one to three hours. Most residents are prepared to deal with this.

Wildfires occur primarily during drought conditions. Wildfires can cause extensive damage, both to property and human life, and can occur anywhere in the county. Even though wildfires can have various beneficial effects on wilderness areas for plant species that are dependent on the effects of fire for growth and reproduction, large wildfires often have detrimental atmospheric consequences, and too frequent wildfires may cause other negative ecological effects. Current techniques may permit and even encourage fires in some regions as a means of minimizing or removing sources of fuel from any wildfire that might develop.

Since there are no remote forested regions in Clark County, wildfires can be easily spotted and are capable of being maintained. The County does not have any areas that are considered wild land-urban interface because property outside city limits is primarily agricultural land, thus, there are no urban interface areas of risk in the County. In addition, fire interference with traffic on highways is not a major concern. The most important factor in mitigating against wildfires continues to be common sense and adherence to burning regulations and suggestions disseminated by the County.

Moisture amounts have the biggest impact on fire situations. During wet years, fire danger is low. More controlled burns are conducted and fewer mishaps occur. During dry years, severe restrictions are placed on any types of burns. For information on dealing with open/controlled burning within the county, see SDCL 34-29B and SDCL 34-35.

Climate Change is a global issue. Climate change exacerbates many of the identified weather hazards such as drought, extreme temperatures, severe storms, flooding, tornadoes and wildfires. Current climate conditions in the northern Great Plains already put a strain on communities and cause millions of dollars in damages. Climate change will only add to these problems.

ASSESSING VULNERABILITY: NATIONAL FLOOD INSURANCE PROGRAM COMPLIANCE

Requirement 201.6(c)(3)(ii).  Local Mitigation Plan Review Tool – C2.

Clark County participates in the National Flood Insurance Program (NFIP). The City of Clark, Raymond and Willow Lake has been mapped and participates in the NFIP. Table 4.14 shows County entities that participate in the NFIP.

Table 4.14: Communities Participating in the National Flood Program, Clark County, SD

| Community Name | Community ID | Current Map Effective Date |
| --- | --- | --- |
| City of Clark | 460013 | 07/01/1998 |
| City of Raymond | 461205 | 06/08/1998 |
| Town of Willow Lake | 460014 | 07/01/1998 |

ADDRESSING VULNERABILTY: REPETITIVE LOSS PROPERTIES

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B4.

Due to various geomorphologic and topographical conditions, periodic flooding affects numerous areas in both incorporated and unincorporated areas of the County. The City of Clark, Raymond, and Willow Lake all have identified Flood Hazard Areas. See Table 4.15 for County NFIP statistics.

Table 4.15: Clark County National Flood Insurance Program Statistics

| Community Name | Current NFIP Policies | Number of Claims Paid Since 1978 | Total Value of Claims Paid | Policies for Structures in A-Zones | Repetitive Loss Properties |
| --- | --- | --- | --- | --- | --- |
| Clark County | 2 | 6 | $142,000.00 | 0 | 1 |
| Clark | 9 | 0 | 0 | 8 | 0 |
| Raymond | 0 | 0 | 0 | 0 | 0 |
| Willow Lake | 2 | 3 | $42,850.20 | 0 | 1 |

SOURCE: South Dakota State NFIP Coordinator (2018)

An issue of concern for the PDM Planning Team is the number of times specific properties and structures on those properties flood. As of 2018, Clark County had experienced 2 repetitive loss claims over two properties. Those properties have been paid a total of $184,500. Repetitive loss properties are those for which two or more losses of at least $1,000 each have been paid under the National Flood Insurance Program (NFIP) within any ten-year period. A goal of the County is to protect specific areas in the county from flooding. This goal aims to protect properties prone to flood losses but does not discount the possibility that in some cases structures located in the floodplain may need to be removed.

ADDRESSING VULNERABILTY: SEVERE REPETITIVE LOSS PROPERTIES

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B4.

The Flood Insurance Reform Act of 2004 identified another category of repetitive loss, severe repetitive loss, and defined it as “a single family property (consisting of one-to-four residences) that is covered under flood insurance by the NFIP and has incurred flood-related damage for which four or more separate claims payments have been paid under flood insurance coverage with the amount of each claim payment exceeding $5,000 and with cumulative amount of such claims payments exceeding $20,000; or for which at least two separate claims payments have been made with the cumulative amount of such claims exceeding the reported value of the property. Since Clark County does not have any properties classified “severe repetitive loss.”

ASSESSING VULNERABILITY: IDENTIFYING STRUCTURES

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B3.

One of the primary purposes of this PDM is identifying critical facilities, emergency shelters, and summer storm shelters and equipping those facilities with the means to provide the necessary energy for access to sanitation and maintain important functions during a natural hazard occurrence. In the event of a disaster as a result of severe summer or winter storms, flooding, or utility interruption the County and participating entities will have the ability to prevent further loss of life by generator powered critical facility shelters. Each jurisdiction was responsible for listing critical infrastructure within their communities. Table 4.16 is a list of critical facilities that would cause the greatest distress in the county if destruction occurred. The information provided in Table 4.16 was compiled via survey of the participating communities.

Table 4.16: Critical Structures in Clark County

| Jurisdiction/ Entity | Location | Address | Sector | Sub Sector | Name | Owner Type |
| --- | --- | --- | --- | --- | --- | --- |
| Clark County | Clark County | 42563 168th St | Population to Protect | Recreation | Oak Tree Hunting Lodge | Private |
| Clark County | Clark County | Various Locations | Communication | Telecommunications | Cell tower | Private |
| Clark County | Clark County | Various Locations | Population to Protect | Private Institution | Hutterite Colonies | Private |
| Clark County | Clark County | Various Locations | Energy | Gas Pipeline | Keystone Pipeline Valves | Private |
| Clark County | Clark County | 42617 183rd St | Population to Protect | Recreation | Double P Ranch | Private |
| Clark County | Clark County | 160 St & 421st Ave | Emergency Fuel Facility | Gas Plant | Crocker Gas Plant | Private |
| Clark County | Clark County | 1531 426th St | Government Facility | Airport | Clark Airport | Private* |
| Town of Bradley | Bradley | 204 Main St | Government Facility | Building | Fire Hall/Community Room | Public |
| Town of Bradley | Bradley | 202 Main St | Government Facility | Building | City Hall | Public |
| Town of Bradley | Bradley | 201 Main St | Telecommunications | Building | ITC Building | Private |
| Town of Bradley | Bradley | 214 Main St | Government Facility | Building | US Post Office | Public |
| Town of Bradley/Clark County | Bradley | 425 Railway St | Government Facility | Building | County Highway Maintenance Shop | Public |
| Town of Bradley | Bradley | 227 3rd St | Public Institution | Building | Christian School | Private |
| City of Clark | Clark | 120 N Commercial St | Government Facility | Building | City Hall/Community Center/Police Station | Public |
| City of Clark | Clark | 227 Clausen Ave | Government Facility | Building | City Maintenance Shop/Fire Hall | Public |
| City of Clark | Clark | 100 North Cloud St | Population to Protect | Recreation | Park | Public |
| City of Clark | Clark | 535 5th Ave SE | Government Facility | Sanitary Sewer | Wastewater Treatment Plant | Public |
| City of Clark | Clark | 135 N Kansas St | Government Facility | Water Supply | Water Treatment Plan | Public |
| Jurisdiction/ Entity | Location | Address | Sector | Sub Sector | Name | Owner Type |
| City of Clark | Clark | 200 N Clinton St | Population to Protect | Recreation | Park | Public |
| City of Clark | Clark | 310 N Utah St. | Population to Protect | Recreation | Swimming Pool/Park | Public |
| City of Clark | Clark | 222 Clausen Ave | Government Facility | Building | Medical Van Garage | Public |
| City of Clark | Clark | SW corner of N Utah St & 3rd Ave NW | Non-Emergency Facility | Water Supply | Water Tower | Public |
| City of Clark | Clark | 210 N Idaho St | Population to Protect | Building | Clark Elementary School | Public |
| City of Clark | Clark | 220 N Clinton | Population to Protect | Building | Clark High School | Public |
| City of Clark | Clark | 211 N Commercial | Population to Protect | Building | Clark Clinic | Private* |
| City of Clark | Clark | 201 8th Ave NW | Population to Protect | Building | Clark Care Center | Private* |
| City of Clark | Clark | 108 S Smith St | Population to Protect | Building | Assisted Living Center (Rotells) | Private |
| City of Clark | Clark | 700 N Smith Street | Population to Protect | Building | Assisted Living Center (Wookeys) | Private |
| City of Clark | Clark | 101 & 103 S Commercial St | Population to Protect | Building(s) | City View Apartments | Private |
| City of Clark | Clark | 221 S Cloud St | Population to Protect | Building(s) | Viking Apartments | Private |
| City of Clark | Clark | 402 N Dakota St | Population to Protect | Building(s) | Colonial Apartments | Private |
| City of Clark | Clark | 400 S Commercial St | Population to Protect | Building(s) | Griffin Apartments | Private |
| City of Clark | Clark | 117 1st Ave W | Population to Protect | Building(s) | Little Explorers Daycare | Private |
| City of Clark | Clark | 204 S Dakota St | Population to Protect | Building(s) | Hallstrom Daycare | Private |
| City of Clark | Clark | 114 S Commercial St | Population to Protect | Building(s) | Angie’s Daycare | Private |
| City of Clark | Clark | 410 N Kansas St | Population to Protect | Building(s) | Lasortune Daycare | Private |
| City of Clark | Clark | 529 1st Ave E | Population to Protect | Building(s) | Mobile Home Park | Private |
| Jurisdiction/ Entity | Location | Address | Sector | Sub Sector | Name | Owner Type |
| City of Clark | Clark | 408 1st Ave W | Population to Protect | Building(s) | Hotel(s)/Motel(s) | Private |
| Town of Garden City | Garden City | SE Corner of Main St. & Grover St. | Government Facility | Fire Hall/City Building | Fire Hall/City Building | Public |
| Town of Garden City | Garden City | SE corner of 1st St. NE & Hayward Ave | Non-Emergency Facility | Sanitary Sewer | Lift Station | Public |
| Town of Garden City | Garden City | ¼ mile west of 432nd Ave & 168th St. | Non-Emergency Facility | Sanitary Sewer | Sewer Lagoon | Public |
| Town of Garden City | Garden City | South of City Park between Hayward Ave & McKinley Ave | Non-Emergency Facility | Water Supply | Well(s) | Public |
| Town of Garden City | Garden City | 1900 Grover Ave | Population to Protect | Recreation | Prairie Ridge Lodge | Private |
| Town of Garden City | Garden City | Hayward Ave & Main St. | Population to Protect | Recreation | School Park | Public |
| Town of Garden City | Garden City | South of Main Street between Hayward Ave & McKinley Ave | Population to Protect | Recreation | City Park | Public |
| Town of Naples | Naples | N ½ OF Section 14-115-56 | Non-Emergency Facility | Waste Disposal | Tree Dump | Public |
| Town of Raymond | Raymond | 206 Ranney Ave | Government Facility | Water Supply | Water Towner/Pump House | Public |
| Town of Raymond | Raymond | 201 Flower St | Government Facility | Building | Fire Hall/Community Room | Public |
| Town of Raymond | Raymond | 206 Ranney Ave | Government Facility | Sanitary Sewer | Lift Station | Public |
| Town of Raymond | Raymond | 301 Yost Ave | Government Facility | Building | County Shop | Public |
| Town of Raymond | Raymond | 201 Private Ave | Telecommunications | Building | ITC Building | Private |
| Town of Raymond | Raymond | 202 Flower St | Population to Protect | Building | Bethke Lodge | Private |
| Town of Raymond | Raymond | 414th Ave | Non-Emergency Facility | Energy | Community Oil (Propane) | Private |
| Jurisdiction/ Entity | Location | Address | Sector | Sub Sector | Name | Owner Type |
| Town of Raymond | Raymond | 202 Ranney Ave | Non-Emergency Facility | Energy | Community Oil Bulk Tanks | Private |
| Town of Vienna | Vienna | Main St & Milwaukee Ave. | Government Facility | Building | Town Hall | Public |
| Town of Vienna/Clark County | Vienna | 314 Main St | Government Facility | Building | County Shed | Public |
| Town of Vienna | Vienna | Main St & Dakota Ave. | Population to Protect | Recreation | Park | Public |
| Town of Vienna | Vienna | SW corner of Main St. & Dakota Ave. | Government Facility | Building | Fire Hall | Public |
| Town of Vienna | Vienna | ½ block West of Clark Ave & Main St. | Government Facility | Building | Town Shed | Public |
| Town of Vienna | Vienna | 407 Clark Ave | Population to Protect | Building | Lutheran Church | Private |
| Town of Vienna | Vienna | NE corner of Clark Ave & Howe Dr. | Telecommunication | Building | ITC Building | Private |
| City of Willow Lake | Willow Lake | 211 Garfield Ave | Government Facility | Building | City Office | Public |
| City of Willow Lake | Willow Lake | 310 Garfield Ave | Government Facility | Building | City Shop/Water Tower | Public |
| City of Willow Lake | Willow Lake | 110 Garfield Ave | Non-Emergency Facility | Building | Fire & Emergency Services | Public |
| City of Willow Lake | Willow Lake | 213 Garfield Ave | Population to Protect | Building | Community Center | Public |
| City of Willow Lake | Willow Lake/Clark County | SE ½ in Section 33-114-57 | Non-Emergency Facility | Water Supply | City Water Supply | Public |
| City of Willow Lake | Willow Lake | 2nd Ave & Dexter St | Non-Emergency Facilities | Sanitary Sewer | Lift Station(s) | Public |
| City of Willow Lake | Willow Lake | 400 Garfield Ave | Population to Protect | Building | Willow Lake High School | Public |
| City of Willow Lake | Willow Lake | 400 Grant Ave | Population to Protect | Recreation | Swimming Pool | Public |
| City of Willow Lake | Willow Lake | 415 Lincoln Ave | Population to Protect | Recreation | City Park | Public |
| Jurisdiction/ Entity | Location | Address | Sector | Sub Sector | Name | Owner Type |
| City of Willow Lake | Willow Lake | 400 Grant Ave | Population to Protect | Recreation | Baseball Field | Public |
| City of Willow Lake | Willow Lake | 310 Garfield Ave | Non-Emergency Facility | Sanitary Sewer | Wastewater plant | Public |
| City of Willow Lake | Willow Lake | 320 Garfield Ave | Non-Emergency Facility | Building | School Shop | Public |
| City of Willow Lake | Willow Lake | 400 Jackson Ave | Non-Emergency Facility | Building | Garage | Public |
| City of Willow Lake | Willow Lake/Clark County | North 3rd Street | Non-Emergency Facility | Building | County Highway Shop | Public |
| City of Willow Lake | Willow Lake | 214 Garfield | Government Facility | Building | US Post Office | Public |
| City of Willow Lake | Willow Lake | 111 Elevator Road | Non-Emergency Facility | Energy | Agtegra | Private |
| City of Willow Lake | Willow Lake | 302 3rd St | Population to Protect | Community Day Care | Day Care | Public* |

| Location | Address (Appendix F) | Sector | Subsector | Name | Owner Type |
| --- | --- | --- | --- | --- | --- |
| Blaine Township | Map1 | Utility | OH Powerlines | 9 miles | Public |
| Cottonwood Township | Map 2 | Utility | OH Powerlines | 9 miles | Public |
| Spring Valley Township | Map 3 | Utility | OH Powerlines | 5 miles | Public |
| Warren Township | Map 4 | Utility | OH Powerlines | 7 miles | Public |
| Ash Township | Map 5 | Utility | OH Powerlines | 2 miles | Public |
| Woodland | Map 6 | Utility | OH Powerlines | 9 miles | Public |
| Thorp Township | Map 7 | Utility | OH Powerlines | 12 miles | Public |
| Location | Address (Appendix F) | Sector | Subsector | Name | Owner Type |
| Maydel Township | Map 8 | Utility | OH Powerlines | 7 miles | Public |
| Eden Township | Map 9 | Utility | OH Powerlines | 2 miles | Public |
| Mt Pleasant Township | Map 10 | Utility | OH Powerlines | 7 miles | Public |
| Garfield Township | Map 11 | Utility | OH Powerlines | 12 miles | Public |
| Raymond Township | Map 12 | Utility | OH Powerlines | 14 miles | Public |
| Logan Township | Map 13 | Utility | OH Powerlines | 15 miles | Public |
| Lincoln Township | Map 14 | Utility | OH Powerlines | 15 miles | Public |
| Day Township | Map 15 | Utility | OH Powerlines | 4 miles | Public |
| Elrod Township | Map 16 | Utility | OH Powerlines | 0 miles | Public |
| Foxton Township | Map 17 | Utility | OH Powerlines | 0 miles | Public |
| Merton Township | Map 18 | Utility | OH Powerlines | 3 miles | Public |
| Darlington Township | Map 19 | Utility | OH Powerlines | 9 miles | Public |
| Fordham Township | Map 20 | Utility | OH Powerlines | 4 miles | Public |
| Richland Township | Map 21 | Utility | OH Powerlines | 8 miles | Public |
| Hague Township | Map 22 | Utility | OH Powerlines | 2 miles | Public |
| Lake Township | Map 23 | Utility | OH Powerlines | 3 miles | Public |
| Location | Address (Appendix F) | Sector | Subsector | Name | Owner Type |
| Pleasant Township | Map 24 | Utility | OH Powerlines | 2 miles | Public |
| Washington Township | Map 25 | Utility | OH Powerlines | 9 miles | Public |
| Collins Township | Map 26 | Utility | OH Powerlines | 8 miles | Public |
| Rosedale Township | Map 27 | Utility | OH Powerlines | 4 miles | Public |

ASSESSING VULNERABILITY: COMMUNITY CAPABILITIES

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B1.

Each community has a unique set of capabilities, including authorities, policies, programs, staff, funding, and other resources for accomplishing mitigation.  One important step in assessing the vulnerability of a given community is to objectively review the capabilities to implement mitigation strategies and to identify limiting factors. Each community reviewed existing administrative documents, procedures, and policies.  This helped the communities and planning team to evaluate how existing capabilities contribute to the vulnerability by reducing or exacerbating disaster impacts. Table 4.17 identifies whether each community has the specified administrative and technical capabilities, and who serves in such capacity. Table 4.18 encapsulates the efficacy of the specified planning mechanisms with regard to disaster mitigation and to identify potential deficiencies in the specified plans.

Table 4.17: Administrative and Technical Capabilities

| Administrative/ Staff Composition | Local Jurisdiction |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Bradley | Clark (City) | Garden City | Naples | Raymond |
| Board of Adjustment | NA | Elected Officials | NA | NA | NA |
| Building Official | NA | NA | NA | NA | NA |
| Community Planner | NA | NA | NA | NA | NA |
| Elected Officials | Trustee | Aldermanic | Trustee | Trustee | Trustee |
| Emergency Manager | NA | NA | NA | NA | NA |
| Engineer/Highway Superintendent | NA | Appointed | NA | NA | NA |
| Floodplain Administrator | NA | Finance Officer | NA | NA | NA |
| GIS Coordinator | NA | NA | NA | NA | NA |
| Planning Commission | NA | Elected Officials | NA | NA | NA |
| Zoning Officer | NA | Finance Officer | NA | NA | NA |
| Grant Writing Capability (Yes/No) | Yes* | Yes* | Yes* | Yes* | Yes* |
| Non-profit organizations focused on environmental protection. | Yes** | Yes** | Yes** | Yes** | Yes** |
| Public-Private partnership initiatives addressing disaster-related issues | No | No | No | No | No |
| NA: This jurisdiction has nobody serving in this role. *First District Association of Local Governments provides these services without cost. **East Dakota Watershed Development District. |

Table 4.17: Administrative and Technical Capabilities (continued)

| Administrative/ Staff Composition | Local Jurisdiction |  |  |
| --- | --- | --- | --- |
|  | Vienna | Willow Lake | Clark (County |
| Board of Adjustment | Elected Officials | Elected Officials | Elected Officials |
| Building Official | NA | NA | NA |
| Community Planner | NA | NA | NA |
| Elected Officials | Trustee | Aldermanic | Commission |
| Emergency Manager | NA | NA | Appointed |
| Engineer/Highway Superintendent | NA | NA | Appointed |
| Floodplain Administrator | NA | Finance Officer | NA |
| GIS Coordinator | NA | NA | NA |
| Planning Commission | Elected Officials | Elected Officials | Elected Officials |
| Zoning Officer | Finance Officer | Finance Officer | Appointed (Director of Equalization) |
| Grant Writing Capability (Yes/No) | Yes* | Yes* | Yes* |
| Non-profit organizations focused on environmental protection. | Yes** | Yes** | Yes** |
| Public-Private partnership initiatives addressing disaster-related issues | No | No | No |
| NA: This jurisdiction has nobody serving in this role. *First District Association of Local Governments provides these services without cost. **East Dakota Watershed Development District. |

Table 4.18: Capabilities of Growth Guidance Instruments

| Capabilities of Community Planning Mechanisms | Bradley | Clark (City) | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Does the Future Land-Use Map identify natural hazard areas? | NA | Y | NA | NA | NA | Y | Y | Y |
| Do the land-use policies discourage development or redevelopment within natural hazard areas? | NA | Y | NA | NA | NA | Y | Y | Y |
| Does the plan provide adequate space for expected future growth in areas located outside natural hazard areas? | NA | Y | NA | NA | NA | Y | Y | Y |
| Does the transportation plan limit access to hazard areas? | NA | N | NA | NA | NA | N | N | N |
| Is transportation policy used to guide growth in safe locations? | NA | Y | NA | NA | NA | Y | Y | Y |
| Are movement systems designed to function under disaster conditions (e.g. evacuation)? | NA | Y | NA | NA | NA | Y | Y | Y |
| Are environmental systems that protect development from hazards identified and mapped? | NA | N | NA | NA | NA | N | N | N |
| Do environmental policies provide incentives to development that is located outside protective ecosystems? | NA | N | NA | NA | NA | N | N | N |
| Do environmental policies maintain and restore protective ecosystems? | NA | N | NA | NA | NA | N | N | N |
| Are the goals and policies of the comprehensive plan related to those of the FEMA Local Hazard Mitigation Plan? | NA | N | NA | NA | NA | N | N | N |
| Is safety explicitly included in the plan's growth and development policies? | NA | Y | NA | NA | NA | Y | Y | Y |

Table 4.18: Capabilities of Growth Guidance Instruments (continued)

| Capabilities of Community Planning Mechanisms | Bradley | Clark (City) | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Does the monitoring and implementation section of the plan cover safe growth objectives? | NA | N | NA | NA | NA | N | N | N |
| Does the Zoning Ordinance conform to the comprehensive plan in terms of discouraging development or redevelopment within natural hazard areas? | NA | Y | NA | NA | NA | Y | Y | Y |
| Does the zoning ordinance contain natural hazard overlay zones that set conditions for land use within such zones? | NA | Y | NA | NA | NA | Y | Y | Y |
| Do rezoning procedures recognize natural hazard areas as limits on zoning changes that allow greater intensity or density of use? | NA | Y | NA | NA | NA | Y | Y | Y |
| Does the zoning ordinance restrict development within, or filling of, wetlands, floodways, and floodplains? | NA | Y | NA | NA | NA | Y | Y | Y |
| Do the subdivision regulations restrict the subdivision of land within or adjacent to natural hazard areas? | NA | Y | NA | NA | NA | NA | Y | NA |
| Do the subdivision regulations provide for conservation subdivisions or cluster subdivisions in order to conserve environmental resources? | NA | N | NA | NA | NA | NA | N | NA |
| Do the subdivision regulations allow density transfers where Hazard areas exist? | NA | N | NA | NA | NA | NA | N | NA |

NA: This jurisdiction does not have the specified document.

ASSESSING VULNERABILITY: ESTIMATING POTENTIAL LOSSES

Requirement 201.6(b)(3).  Local Mitigation Plan Review Tool – A4.

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B3.

Requirement 201.6(d)(3).  Local Mitigation Plan Review Tool – D1.

The 2013 Plan provided some specific information regarding potential losses. As part of this Plan, the Planning Team decided to include estimates for number of structures, value of structures, and the percentage of which are located within identified hazard areas. These estimates shall be used in multiple ways, including the establishment of baseline statistics for future development and disaster mitigation plans. The information provided in the following tables was collected from the Clark County Director of Equalization. Inconsistencies and missing information result from lack of existing mechanisms, plans, and technical documents available.

The assessor’s office provided the assessed valuation of total structures on each property within the incorporated and rural areas of the county. The data provides a total value for structures of a certain use on each property.  It was not possible to discern the value of each structure on a lot, so the actual number of structures is based on the number of parcels with the specified use type. For the purposes of this plan only Residential, Commercial/Industrial, Agricultural, and Manufactured Homes were included. More specifically, all agricultural structures were included; only primary residential structures (houses, apartments, etc.) and not including sheds, lean-to’s, and garages were included. All commercial or industrial structures were included, whether considered primary or accessory structures. Public or quasi-publicly owned structures and other structures for which the Department of Equalization did not have an assessed value were not included in the calculation. Structures throughout the incorporated and unincorporated portions of the county were reviewed based upon updated flood hazard area (Zone “A”) boundaries and other discovery documents provided by FEMA in 2017 based upon 2016 base level engineering. (Please note: during the course of this project, updated base level engineering was used to generate new versions of the maps used for analysis.  As a result, any structures located in the orange colored areas on the map were considered in Zone A but may be removed at the time of adoption of this plan.)   Since structural values were not readily available on a parcel by parcel basis; an average value for each land use type was generated by jurisdiction and multiplied by the number of parcels with structures occupied by the specified use within that jurisdiction. The analysis does not account for letters of map amendment or letters of map revision which may have been approved.

Figure 4.1 Clark County Flood Hazard Vulnerability Map

All properties with structures, whether owner occupied or not were included in the valuations provided in Tables 4.19 through 4.28. The reports provided by the assessor’s office did not include the number of people in each structure; thus, many of the tables are missing this information. It should be noted that the number of structures references the number of parcels with structures of a certain land use category. In cases where a residential use and commercial use occupy the same parcel, they are counted under each category. Some parcels with “Residential” structures only include garages/storage buildings or other accessory structures but no residence. To determine the number of people in the hazard area, the number of housing units located in the hazard area was multiplied by the average number of residences per household in the unincorporated portion of the county as well as each respective municipality.  The following tables also do not address information regarding religious, governmental, or utility structures. Although not included in Tables 4.19 through 4.28, the State of South Dakota Hazard Mitigation Plan incorporated HAZUS analysis accounting for potential losses to those structures within Clark County.

Table 4.19: Clark County (Rural Area) Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in County | # in HA | % in HA | $ in County | $ in HA | % in HA | # in Rural Areas | # in HA | % in HA |
| Residential | 2,824 | 223 | 7.9 | $299,349,147 | $12,602,118 | 4.2 | 4,121 | 513 | 12.4 |
| Commercial/Industrial | 182 | 6 | 3.3 | $25,079,224 | $788,600 | 3.1 |  |  |  |
| Agricultural | 986 | 21 | 2.1 | $14,195,163 | $297,300 | 2.1 |  |  |  |
| Mobile Homes | 265 | 21 | 7.9 | $25,079,224 | $440,233 | 1.8 |  | 48 | 1.2 |
| Total | 4,257 | 271 | 6.4 | $344,202,027 | $14,128,251 | 4.1 | 4,121 | 561 | 13.6 |

Table 4.20: Bradley Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 66 | 0 | 0 | $822,622 | 0 | 0 | 72 | 0 | 0 |
| Commercial/Industrial | 6 | 0 | 0 | $43,340 | 0 | 0 |  |  |  |
| Agricultural | 2 | 0 | 0 | $99,415 | 0 | 0 |  |  |  |
| Manufactured Home | 3 | 0 | 0 | $50,000 | 0 | 0 |  |  |  |
| Total | 77 | 0 | 0 | $1,015,377 | 0 | 0 | 72 | 0 | 0 |

Table 4.21: Clark (City) Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 505 | 68 | 13.5 | $21,657,886 | $2,916,309 | 13.5 | 1,139 | 141 | 12.4 |
| Commercial/Industrial | 86 | 33 | 38.4 | $6,504,766 | $2,496,015 | 38.4 |  |  |  |
| Agricultural | 3 | 0 | 0.0 | $25,495 | $0 | 0.0 |  |  |  |
| Manufactured Home | 23 | 11 | 47.8 | $492,115 | $235,359 | 47.8 |  | 22 | 1.9 |
| Total | 617 | 112 | 18.2 | $28,680,262 | $5,647,683 | 19.7 | 1,139 | 163 | 19.7 |

Table 4.22: Garden City Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 41 | 2 | 4.9 | $282,031 | $13,758 | 4.9 | 53 | 5 | 9.4 |
| Commercial/Industrial | 14 | 2 | 14.3 | $2,029,810 | $289,973 | 14.3 |  |  |  |
| Agricultural | 4 | 1 | 25.0 | $57,022 | $10,319 | 25.0 |  |  |  |
| Manufactured Home | 3 | 0 | 0 | $29,730 | 0 | 0 |  | 0 | 0 |
| Total | 62 | 5 | 8.1 | $2,398,593 | $314,050 | 13.0 | 53 | 5 | 9.4 |

Table 4.23: Naples Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 17 | 0 | 0 | $115,354 | 0 | 0 | 41 | 0 | 0 |
| Commercial/Industrial | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Agricultural | 2 | 0 | 0 | $14,860 | 0 | 0 |  |  |  |
| Manufactured Home | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |
| Total | 19 | 0 | 0 | $130,214 | 0 | 0 | 41 | 0 | 0 |

Table 4.24: Raymond Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 50 | 4 | 8.0 | $504,034 | $40,323 | 8.0 | 50 | 7 | 14.0 |
| Commercial/Industrial | 10 | 1 | 10 | $119,356 | $11,935 | 10.0 |  |  |  |
| Agricultural | 4 | 0 | 0 | $41,275 | $0 | 0 |  |  |  |
| Manufactured Home | 5 | 2 | 40.0 | $76,375 | $30,550 | 40.0 |  | 4 | 8.0 |
| Total | 69 | 7 | 10.1 | $741,040 | $82,808 | 16.3 | 50 | 11 | 22.0 |

Table 4.25: Vienna Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 37 | 0 | 0 | $288,454 | 0 | 0 | 45 | 0 | 0 |
| Commercial/Industrial | 8 | 0 | 0 | $406,045 | 0 | 0 |  |  |  |
| Agricultural | 3 | 0 | 0 | $5,461 | 0 | 0 |  |  |  |
| Manufactured Home | 3 | 0 | 0 | $11,000 | 0 | 0 |  |  |  |
| Total | 51 | 0 | 0 | $710,960 | 0 | 0 | 45 | 0 | 0 |

Table 4.26: Willow Lake Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in City | # in HA | % in HA | $ in City | $ in HA | % in HA | # in City | # in HA | % in HA |
| Residential | 137 | 19 | 13.9 | $3,657,766 | $507,281 | 13.9 | 263 | 43 | 16.3 |
| Commercial/Industrial | 31 | 6 | 19.4 | $1,561,728 | $302,270 | 19.4 |  |  |  |
| Agricultural | 0 | 0 | 0 | $0 | $0 | 0 |  |  |  |
| Manufactured Home | 8 | 6 | 75.0 | $182,031 | $136,523 | 75.0 |  | 13 | 5.0 |
| Total | 176 | 31 | 17.6 | $5,401,525 | $946,074 | 17.5 | 263 | 56 | 21.3 |

Table 4.27: Clark County Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Number of Structures |  |  | Value of Structures |  |  | Number of People |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # in County | # in HA | % in HA | $ in County | $ in HA | % in HA | # in County | # in HA | % in HA |
| Residential | 5,189 | 456 | 8.8 | $485,298,373 | $25,286,318 | 5.2 | 11,200 | 1,026 | 9.2 |
| Commercial/Industrial | 592 | 42 | 7.1 | $101,864,424 | $10,788,400 | 10.6 |  |  |  |
| Agricultural | 999 | 25 | 2.5 | $14,425,463 | $297,300 | 2.1 |  |  |  |
| Manufactured Home | 398 | 30 | 7.5 | $7,071,563 | $599,690 | 8.5 |  | 70 | 0.6 |
| Total | 7,718 | 555 | 7.2 | $610,659,823 | $36,703,708 | 6.0 | 11,200 | 1,096 | 9.8 |

Table 4.28 is an overall summary of vulnerability by utility provider produced from information gathered from the providers.

Table 4.28: Electrical Utilities Estimated Potential Dollar Losses to Vulnerable Structures

| Type of Structure | Utility Provider | Total Number of Structures | Total Value of Structures | HAZARDS (Yes or No) |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Flood | Strong Winds | Tornado | Winter Storms |
| Poles | Codington-Clark | 3700 | $3,330,000.00 | X | X | X | X |
| Overhead Transformers | Codington-Clark | 147 | $132,300.00 | X | X | X | X |
| Underground Transformers | Codington-Clark | 1100 | $990,000.00 | X |  | X |  |
| Underground Cabinets | Codington-Clark | 75 | $67,500.00 | X |  | X |  |
| Underground Pedestals | Codington-Clark | 1476 | $1,771,200.00 | X |  | X |  |
| Miles of Underground Line | Codington-Clark | 492 | $15,744,000.00 | X |  |  |  |
| Miles of Overhead Line | Codington-Clark | 181 miles | $1,911,360.00 | X | X | X | X |
| Substations |  |  |  |  |  |  |  |

SOURCE: Codington-Clark Electric Cooperative

Notes:

# in HA: Number of structures in hazard area was determined using aerial photography and Discovery Maps with identified Zone A Hazard Areas based upon 2016 Base Level Engineering provided by FEMA.  Some structures included may have received LOMA’s, removing them from the flood plain, since the effective date of the current DFIRM.  It should also be noted that following the completion of this review, FEMA has updated its base level engineering which resulted in the removal of many structures from Zone A of the Discovery Maps.  The above tables were based upon the 2016 Data because the 2018 data was not available in a format compatible with the means by which this report was completed in time for the completion of this plan.

$ in HA: Value of structures in hazard area was estimated by extrapolating assessed valuations of structures on parcels which had a primary structure of the given use type within the hazard area.  Because data was not available on a property by property basis, an average value of structures on a lot of each specific use type was determined based upon data supplied by the Clark County Department of Equalization and multiplied by the number of parcels with structures within the flood hazard area for each given use type.

# in [Jurisdiction]: The number of people was based on the 2010 Census.

# in Hazard Area: The number of people in a hazard area was determined by multiplying the average household size of a given community as identified by the number of structures in the identified hazard area and multiplying that number by the rate of occupancy for the community (All statistics from the US Census 2010).

As part of the State of South Dakota Hazard Mitigation Plan, data was prepared for specific hazard types. Although the data is not current, the modeling used in the plan would be difficult to replicate or improve upon. The following sections describing vulnerability to flooding and tornadoes is based largely on the corresponding sections in the State of South Dakota Hazard Mitigation Plan.

Flooding

A portion of Clark County is in the Big Sioux River Watershed therefore Clark County was included within the Big Sioux Region in the State of South Dakota Hazard Mitigation Plan. Based on its history of flood problems, the County was deemed a high priority jurisdiction in South Dakota’s Plan.  For that reason, HAZUS-MH analysis was performed in conjunction with the completion of the State’s Plan. The results were based on flooding with a one percent chance of occurrence or commonly referred to as a “100-year flood” and display the potential base flood losses to the County. The full results of HAZUS-MH analysis for the County are displayed in Table 4.29

FEMA updated the HAZUS modeling based on 2010 Census information as part of a nationwide study. Data from Clark County was extracted to produce a specified report for the purposes of this plan. It should be noted that the data represented in Figure 4.1 is intended to identify those areas most prone to flooding in Clark County, rather than to provide a precise prediction of losses in a base flood (1 percent chance). Since no flood elevations have been established for most portions of Clark County, the HAZUS data, though not precise is the best available data for projecting flood losses in Clark County at the present time.

Table 4.29:  HAZUS-MH Base Flood (1 Percent Chance) Loss Estimation Results (2011)

| Building Damage | Loss Ratio* | Contents Damage and Inventory Loss | Total Economic Building Loss | Number of Displaced People | People Needing Shelter |
| --- | --- | --- | --- | --- | --- |
| 2 | 0.5% | $1,880,000 | $3,328,000 | 159 | 45 |

SOURCE: State of South Dakota Hazard Mitigation Plan.  p 3-147; Table 3-41. South Dakota

*Loss ratio is the percent of the total building inventory value that could be damaged from flooding in any given year.

Tornado

As part of the State of South Dakota Hazard Mitigation Plan HAZUS-MH analysis was performed calculating potential building exposure to tornadoes in the state. Total value of structures lost due to tornadoes from 1950 – 2010 was calculated, inflated to current (2009) dollars. A loss ratio was then calculated by dividing the total damage by the total building exposure. Table 4.30 identifies data specific to the annualized losses from tornadoes for the County as identified in the State of South Dakota Hazard Mitigation Plan.

To provide additional insight into potential losses caused by tornadoes, historic loss data were also analyzed on a statewide scale. According to the National Climatic Data Center Storm Events database, there were 1,592 tornadoes in South Dakota between January 1950 and April 2010. Of those, 61 were rated as an F3 event, 6 as an F4, and 1 as an F5. Total property damage for these events is estimated at $643 million. This suggests that South Dakota experiences 10 tornadoes and $10.5 million in losses each year. There were 17 deaths and 441 injuries in this time period, which averages out to approximately eight injuries each year. Of these storms, five resulted in major disaster declarations, with a total relief cost estimated at $148,686,613 in 2008 dollars. This averages out to $29.737 million (also in 2008 dollars) per major disaster. Based on the frequency of events, South Dakota averages one major disaster level tornado every 318 events or approximately every 12 years. The total historic losses and annualized losses by county are presented.

Table 4.30: Clark County Annualized Losses from Tornadoes

| Total Events 1950-2010 | Total Property Damage (inflated) 1950-2010 | Annualized Losses | Total Building Exposure | Loss Ratio |
| --- | --- | --- | --- | --- |
| 23 | $10,846,441 | $180,774 | $250,785,000 | 0.00072 |

SOURCE: State of South Dakota Hazard Mitigation Plan.  P.3-174; Table 3-67. South Dakota Office of Emergency Management 2011.

ASSESSING VULNERABILITY: ANALYZING DEVELOPMENT TRENDS

Requirement 201.6(b)(3).  Local Mitigation Plan Review Tool – A4.

Requirement 201.6(c)(3).  Local Mitigation Plan Review Tool – C1.

Requirement 201.6(d)(3).  Local Mitigation Plan Review Tool – D1.

Requirement 201.6(d)(3).  Local Mitigation Plan Review Tool – D2.

The land use and development trends for each jurisdiction were identified by the representatives from each of the jurisdictions. Multiple communities within Clark County have comprehensive land use plans which identified future areas for development. In addition to Clark County, the municipalities of Clark, Vienna, and Willow Lake have adopted Comprehensive Land Use Plans with Future Land Use Maps. The Comprehensive Land Use Plans for each community were reviewed by each community utilizing one. Specifically, available undeveloped areas projected for residential, commercial, and industrial uses were reviewed. Based upon their own projected density of development for each land use, the communities then identified the potential number of lots which could be created within flood hazard areas given current land use regulations and controls. Tables 4.31 – 4.34 identify the projected vulnerability for communities which have adopted land use plans. Future Land Use Maps for each jurisdiction which have adopted Comprehensive Land Use Plans are included in Appendix G.

Table 4.31: Clark County (Unincorporated Area)

Potential Floodplain Development – By Land Use Type

|  | Community Totals |  | Flood Hazard Area |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Land Use Category | Projected Development Density (Acres/Unit) | Acres of projected future development | Acres of future development in Hazard Area | % Area for future development | Potential # of Lots for future development | # of Undeveloped Lots Already Appropriately Zoned |
| Ag – Residential | 2 | N/A | 124,202 | N/A | 62,101 | 3,868 |
| Lake – Residential | 2 | N/A | N/A | N/A | 0 | 0 |
| Commercial | .25 | N/A | N/A | N/A | 0 | 0 |
| Industrial | .5 | N/A | N/A | N/A | 0 | 0 |
| N/A: Most of the rural area is planned to remain agricultural in use with varying degree of land use restrictions. |  |  |  |  |  |  |

Table 4.32: City of Clark

Potential Floodplain Development – By Land Use Type

|  | Community Totals |  | Flood Hazard Area |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Land Use Category | Projected Development Density (Units/Acre) | Acres of projected future development | Acres of future development in Hazard Area | % Area for future development | Potential # of Lots for future development | # of Undeveloped Lots Already Appropriately Zoned |
| Residential | 2.5 | 43.5 | 14.99 | 34.5 | 86 | 19 |
| Commercial | 1 | 6 | 0.75 | 12.5 | 3 | 3 |
| Industrial | 0.25 | 20 | 2.0 | 10.0 | 2 | 2 |

Table 4.33: Town of Vienna

Potential Floodplain Development – By Land Use Type

|  | Community Totals |  | Flood Hazard Area |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Land Use Category | Projected Development Density (Units/Acre) | Acres of projected future development* | Acres of future development in Hazard Area* | % Area for future development* | Potential # of Lots for future development* | # of Undeveloped Lots Already Appropriately Zoned |
| Residential | 2.5 | 37 | 0 | 0.0 | 0 | 0 |
| Commercial | 1 | 1.5 | 0 | 0.0 | 0 | 0 |
| Industrial | 0.25 | 2.5 | 0 | 0.0 | 0 | 0 |

Table 4.34: City of Willow Lake

Potential Floodplain Development – By Land Use Type

|  | Community Totals |  | Flood Hazard Area |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Land Use Category | Projected Development Density (Units/Acre) | Acres of projected future development | Acres of future development in Hazard Area* | % Area for future development | Potential # of Lots for future development | # of Undeveloped Lots Already Appropriately Zoned** |
| Residential | 2.5 | 50 | 19 | 38.0 | 47 | 0 |
| Commercial | 1 | 6 | 2 | 33.3 | 2 | 0 |
| Industrial | 0.25 | 28 | 24 | 85.7 | 6 | 2 |

UNIQUE OR VARIED RISK ASSESSMENT

Requirement 201.6(c)(2)(i).  Local Mitigation Plan Review Tool – B1.

Requirement 201.6(c)(2)(ii).  Local Mitigation Plan Review Tool – B3.

Requirement 201.6(d)(3).  Local Mitigation Plan Review Tool – D1.

After conducting the risk assessment for each jurisdiction, the PDM Planning Team decided that all areas of the county have an equal chance of a natural hazard occurrence in their area. While the extent to which each jurisdiction is affected by such hazards varies slightly between the local jurisdictions, the implications are the same. Thus, the PDM Planning Team decided that all jurisdictions in the County are equally affected by the types of hazards/risks that affect the PDM jurisdiction. Thus, the unique or varied risk requirement is not applicable to the Clark County PDM.

On the following pages, a hazard vulnerability map is shown for each of the jurisdictions participating in this PDM process. The maps identify critical infrastructure. The maps identify critical infrastructure and one-hundred-year flood plain. Since the other major hazards facing the county are not geographically based. Winter storms and severe summer storms are about as likely to occur in one part of the county as another. Similarly, wildfires can occur almost anywhere in the county, although they are more likely to occur in areas with extensive grassland cover or shrubs. While specific locations for above ground electrical distribution lines are not identified on the map following. They are in Appendix F Codington-Clark Electric Co-Op: Critical Infrastructure/Overhead Power Lines Map Guide

Figure 4.2 Town of Bradley Hazard Vulnerability Map

Figure 4.3 City of Clark Hazard Vulnerability Map

Figure 4.4 Town of Garden City Hazard Vulnerability Map 
Figure 4.5 Town of Naples Hazard Vulnerability Map 
Figure 4.6 Town of Raymond Hazard Vulnerability Map 
Figure 4.7 Town of Vienna Hazard Vulnerability Map

Figure 4.8 City of Willow Lake Hazard Vulnerability Map

Figure 4.9 Clark County Hazard Vulnerability Map

CHAPTER 5

MITIGATION STRATEGY

MITIGATION OVERVIEW

Requirement 201.6(c)(3)(i).  Local Mitigation Plan Review Tool – C3.

Requirement 201.6(c)(3)(ii).  Local Mitigation Plan Review Tool – C4.

Requirement 201.6(c)(3)(iii) & (iv).  Local Mitigation Plan Review Tool – C5.

Requirement 201.6(d)(3).  Local Mitigation Plan Review Tool – D3.

The State Hazard Mitigation Plan addresses several mitigation categories including warning and forecasting, community planning, and infrastructure reinforcement. The County and participating entities’ greatest needs are mitigating high wind and flood hazards, backup generators for critical infrastructure, construction of storm shelters, and public awareness.

After the completion of the risk assessment (identification of hazards, probability of hazards and vulnerability to hazards), it was the mutual consensus of the PDM Planning Team that mitigation strategies of the PDM should focus on the following hazards: winter storms, severe summer storms, flooding, wildfires (urban/rural)

The PDM Planning Team first reviewed the goals, objectives and priorities of the previous Plan. The goals and objectives of the previous plan were incorporated into the goals of this plan. The PDM Planning Team completed the goal identification process by considering the county’s and participating jurisdictions’ vulnerability to each identified hazard, and the severity of the threat posed by each hazard. Much of the discussion focused on damage caused by past events, and what could be done to ensure that future damage will be lessened or eliminated. By reviewing each jurisdiction’s Comprehensive Land Use Plan (if available), the participants also considered how future development might affect the county’s and participating jurisdictions’ vulnerability to the hazards they face. When identifying goals, numerous activities or projects were identified with broadly defined benefits to numerous jurisdictions within the County. Numerous actions were agreed by the PDM Planning Team to have broad reaching benefits but due to scope or varying levels of importance to individual jurisdictions no specific cost, timeframe, or priority was assigned. Likewise, many infrastructure projects and policies throughout all communities would mitigate hazards but were not located in the most vulnerable areas. All communities reviewed the activities/policies and corresponding problem statements to identify whether they applied to their respective jurisdiction. The results of the community review of those general activities/policies are displayed in Tables 5.1 – 5.12. Specific projects for each community are listed in Table 5.13. Those projects intended to mitigate problems at a specific location are represented in Figures 5.1 to 5.8.

Principal Goals

- Reduce the loss of life, property, infrastructure, critical facilities, cultural resources and impacts from severe weather, flooding and other natural disasters.

- Improve public safety during severe weather, flooding and other natural disasters.

- Improve the County’s Emergency Preparedness and Disaster Response and Recovery capabilities.

Mitigation Activities for Flooding Hazards

Goal #1: Protect specific areas of Clark County from flooding.

Goal #2: Educate and inform Clark County residents regarding flooding safety.

Goal #3:	Reduce the extent to which utility interruptions affect areas during flooding events.

- Actions/Projects to reduce flood risk through policy implementation (See Table 5.1)

  - Actions/Projects to change the characteristics or impacts of flood hazards (See Table 5.2)

  - Actions to reduce loss potential of infrastructure to flood hazards (See Table 5.3)

Mitigation Activities for Severe Weather Hazards (summer and winter)

Goal #1: Increase public awareness and education on severe weather issues.

Goal #2: Improve public safety during severe weather.

Goal #3: Reduce the extent to which utility interruptions affect areas during severe weather situations.

Goal #4: Reduce crippling effects of winter storms, especially regarding smaller communities.

- Actions/Projects to reduce severe weather risk through policy implementation (See Table 5.4)

- Actions/Projects to change the characteristics or impacts of severe weather hazards (See Table 5.5)

- Actions/Projects to reduce loss potential of infrastructure to severe weather hazards (See Table 5.6)

Table 5.1: Actions/Projects to Reduce Flood Risk through Policy Implementation

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Public is unaware of scope of flood risk and existing emergency plans | Public education. Disseminate information regarding how to deal with flooding. This would include transportation issues, home protection strategies, safety issues, and how to move forward after a flooding situation. | X | X | X | X | X | X | X | X |  |
|  | Encouraging homeowners in flood-prone areas to purchase flood insurance. | X | X | X | X | X | X | X | X |  |
| Jurisdiction is unaware potential hydrologic impacts of drainage/ development projects | Conduct necessary studies addressing drainage (storm water flow/runoff, etc.). |  |  |  |  |  |  |  |  |
| Residents are not eligible for flood insurance | Begin participation in the National Flood Insurance Program. | X |  | X | X |  | X |  |  |  |
| Failure to comply with NFIP programs makes the community ineligible for flood insurance and certain funding | Ensure continued National Flood Insurance Program compliance by enforcing flood plain management ordinance. |  | X |  |  | X |  | X |  |

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Jurisdiction has no legal mechanism to regulate land use | Adoption and enforcement of land use regulation. | X |  | X | X |  |  |  |  |
| Need to continue to regulate minimum land use and development standards | Continue enforcement of zoning and subdivision ordinances. |  | X |  |  | X | X | X | X |
| Jurisdiction has little legal mechanism to regulate drainage | Developing a county/city drainage ordinance. | X | X | X | X | X | X | X | X |
| Need to continue to regulate minimum construction standards | Continue enforcement of building codes. |  |  |  |  |  |  |  |  |
| No technical analysis or identification of specific mitigation projects | Identify and prioritize capital/structural mitigation projects that are cost effective and technically feasible. | X | X | X | X | X | X | X | X |

Table 5.2: Actions/Projects to Change the Characteristics or Impacts of Flood Hazards

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Portions of storm sewer system is not designed to 100-year flood event | Installing or upgrading storm sewer piping. |  | X |  |  |  |  |  |  |
| Drainage patterns have changed; culverts are inadequate for conveyance of water | Installing or enlarging drainage culverts. | X | X | X | X | X | X |  |  |
| Certain streets have substandard or no curb and gutter | Curbing and guttering of city streets to improve storm water flow. | X | X | X | X | X |  |  |  |
| Capacity of rivers, streams, and retention areas is decreased due to accumulation of debris | Clean out debris in drainage areas, tributaries, etc. to improve water flow | X | X | X | X | X | X |  |  |
| Sanitary and/or storm sewer are vulnerable to back-up in flood event | Install valves, plugs in sanitary and storm sewer system. | X | X |  | X | X |  |  |  |
| Potential for development in flood prone areas. | Preservation and expansion of open space along the river and enhancement of existing berm areas. |  |  |  |  |  |  |  |  |
|  | Work with property owners to implement deed restrictions for open lots/vacant properties in the flood hazard areas to prevent development. |  | X |  |  |  | X |  |  |

Table 5.3: Actions/Projects to Reduce Loss Potential of Infrastructure to Flood Hazards

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Many roads and bridges were built prior to identification of flood hazard areas | Replace and raise bridges |  |  |  |  |  |  |  | X |
|  | Elevating roads in flood-prone areas | X | X | X | X | X | X | X | X |
| Structures constructed in the floodplain prior to identification of flood hazard areas | Making structural retrofits to infrastructure | X | X | X | X | X | X | X | X |

Table 5.4: Actions/Projects to Reduce Severe Weather Risk through Policy Implementation

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Public is unfamiliar with certain disaster preparation measures | Public education. Disseminate information regarding how to deal with severe weather (summer/winter). Some of the issues that may be addressed within the information would include: safety issues on downed power lines, electrical and fire dangers, the necessity for generators and advice on using them, protecting property, survival strategies during storms, and purchasing of back-up power for various household and farming operations. | X | X | X | X | X | X | X | X |
| Lack of data regarding vulnerability to winter storms | Gather data to create a more precise loss estimate for winter storms. | X | X | X | X | X | X | X | X |
| Lack of data regarding vulnerability to summer storms | Gather data to create a more precise loss estimate for summer storms. | X | X | X | X | X | X | X | X |

Table 5.5: Actions/Projects to Change the Characteristics or Impacts of Severe Weather Hazards

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Certain areas and populations are not served by storm shelters | Construct tornado safe rooms or community shelters. | X | X | X | X | X | X | X | X |
|  | Construct storm shelters at manufactured home parks |  | X |  |  |  |  |  |  |
|  | Construct storm shelters at RV parks. |  | X |  |  |  |  | X | X |
| Critical facilities are vulnerable to power failure | Install backup generators | X | X | X | X | X | X | X | X |
| Certain areas are susceptible to snow drifting | Survey areas in need of snow shelterbelts and plant trees accordingly. |  |  |  |  |  |  |  | X |
|  | Install or plant living snow fences |  |  |  |  |  |  |  | X |
| Certain areas of town cannot hear storm sirens and other emergency warning systems | Construct new or improve existing warning systems | X | X | X | X | X | X | X | X |

Table 5.6: Actions/Projects to Reduce Loss Potential of Infrastructure to Severe Weather Hazards

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Utility lines and structures are subject to failure in high wind, heavy rain, ice events | Upgrading of utility lines. | X | X | X | X | X | X | X | X |
|  | Burial of utility lines when needed. | X | X | X | X | X | X | X | X |
|  | Require upgrading of overhead lines when age or disasters provide an opportunity. | X | X | X | X | X | X | X | X |
|  | Removal of trees near power lines. | X | X | X | X | X | X | X | X |
|  | Attachment of guy wires to dead-end poles. | X | X | X | X | X | X | X | X |
|  | Testing integrity of poles | X | X | X | X | X | X | X | X |
|  | Usage of anti-galloping devices | X | X | X | X | X | X | X | X |
|  | Making structural retrofits to facilities. | X | X | X | X | X | X | X | X |

Table 5.7: Actions/Projects to Reduce Fire and Drought Risk through Policy Implementation

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Community becomes vulnerable to fire hazard while staff is being trained. | Find funding sources to pay for persons to fill positions while individuals are at training courses. | X | X | X | X | X | X | X | X |
| Potential for development in areas vulnerable to wildfire or urban fire | Adoption and enforcement of property regulations in areas vulnerable to wildfire. | X | X | X | X | X | X | X | X |
|  | Establish/require minimum fire suppression standards for subdivisions | X | X | X | X | X | X | X | X |
| Community has no plan/policy for water rationing in emergency | Develop water rationing measures that will be implemented during a drought situation. | X | X | X | X | X | X | X | X |
| Public is unaware of benefits of conserving water | Educate residents on the benefits of conserving water at all times, not just during a drought. | X | X | X | X | X | X | X | X |

Table 5.8: Actions/Projects to Reduce Loss Potential of Infrastructure to Fire and Drought Hazards

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Firefighting equipment becomes out of date quickly | Ensure that fire departments are adequately equipped to respond to wildfires | X | X | X | X | X | X | X | X |
| Fire hydrants become unusable | Have rural fire departments locate dry fire hydrants. |  | X |  |  |  |  | X |  |

Table 5.9: Actions/Projects to Change the Characteristics or Impacts of Fire and Drought Hazards

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Dead or dry plant material creates fire hazard/ location changes seasonally and annually | Burn areas to ensure a fire break rather than ignition fuel. |  |  |  |  |  |  |  | X |
| Local economy is very dependent on corn/soybean production | Educate farmers on the benefits of a diversified crop protection plan in the event of a drought | X | X | X | X | X | X | X | X |
|  | Work with local farmers to investigate the use of more drought resistant crops. | X | X | X | X | X | X | X | X |

Table 5.10: Technological Activities

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Current data and software can become obsolete or out of date | Continue utilizing a working computer aided mapping project for the County. This includes using overlays of GIS data, HazMat, and Roads. |  | X |  |  |  |  |  | X |
|  | Enhance existing computer aided dispatch. | X | X | X | X | X | X | X | X |
|  | Use HAZUS software to estimate losses in flooding situations. Information may also be able to be used for other hazard areas. | X | X | X | X | X | X | X | X |

Table 5.11: Planning Activities

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Maintenance of a mitigation plan is beyond the economic capability of this community | Find funding to review and update the regional and local disaster mitigation plans on a five-year cycle. | X | X | X | X | X | X | X | X |
| Disaster mitigation projects have not always been incorporated into other plans | Incorporate disaster mitigation actions into appropriate local and regional plans – Master Plans, land use, transportation, open space, and capital programming. |  | X |  |  |  | X | X | X |
|  | Integrate disaster mitigation concerns into subdivision, site plan review, and other zoning reviews. In particular require the consideration of downstream flooding impacts caused by new projects. |  | X |  |  |  | X | X | X |
|  | Integrate disaster mitigation concerns into transportation projects (e.g. drainage improvements, underground utilities, etc.). |  | X |  |  |  | X | X | X |
| This community's mitigation projects are not coordinated with other communities' projects | Develop a means for sharing information on a regional basis about successful disaster mitigation planning and programs. | X | X | X | X | X | X | X | X |

Table 5.12: Administration/Coordination Activities

| Problem Statements | Actions | Bradley | Clark | Garden City | Naples | Raymond | Vienna | Willow Lake | Clark County |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| This community is not staffed, nor does it have funding mechanisms to apply for and administer funding sources for mitigation projects | Identify and pursue funding that builds local capacity and supports grant-writing for mitigation actions identified in the PDM. | X | X | X | X | X | X | X | X |
| Need to improve coordination of activities with other governmental jurisdictions and utility providers | Increase communication /coordination between federal, state, regional, county, municipal, private, and non-profit agencies in the area of pre-disaster mitigation. | X | X | X | X | X | X | X | X |
|  | Maintain and enhance working relationships with the utility providers. | X | X | X | X | X | X | X | X |

After meetings with the local jurisdictions and opportunities for public input, a series of mitigation goals were devised to best aid the County in reducing and lessening the effects of hazards. Projects previously identified in the 2013 PDM were carefully analyzed and discussed to determine which of the projects had enough merit to be included in the updated PDM and to determine if the projects meet the hazard mitigation needs of the county. These projects were evaluated based on a cost/benefit ratio and priority. Although this PDM focuses on disaster mitigation rather than disaster preparedness, some communities discussed disaster preparedness projects as well. It was difficult for individual communities to recognize the difference between providing storm shelters and making sure the storm shelters function properly (for example). Actions considered in this category included the acquisition of emergency generators, and erecting or replacing warning sirens in areas that currently are not well served.

Most of the mitigation actions proposed by the jurisdictions were identified by city council members, public works personnel, or PDM Planning Team members from the jurisdiction. Some actions were also proposed by townships and utility providers do to the direct impact of disasters on infrastructure and services they provide. Once each jurisdiction had its list of proposed actions complete, it was submitted to the Emergency Management Director. At the second PDM Planning Team meeting, the actions were reviewed, and a final opportunity was given for the jurisdictions to add any additional actions or refine information relating to previously identified projects.

Although in some cases additional data will be necessary, a timeframe for completion, oversight, funding sources, and any other relevant issues were addressed. These implementation strategies are geared toward the specific goal and area. Often, these projects will not encounter any resistance from environmental agencies, legal authorities, and political entities. Table 5.13 is a presentation of the mitigation actions proposed by the PDM Planning Team, County, communities, townships and utility providers. In addition to identifying the proposed actions, the table includes additional information about each action. Elected officials and staff of each municipality and the county were responsible for providing most of this information for actions in their community, but the other planning participants helped in this process. The following information is provided for each action:

- A statement regarding the specific problem the proposed action will mitigate.

- The local priority rating (discussed in the next section).

- The time frame to accomplish the action – “Short” means actions that are intended to be initiated within two years, “Medium” is for actions that should be started within five years, and “Long” is for actions that are not anticipated to be started for at least five years.

- The party(s) primarily responsible for implementing the action.

- The estimated cost - estimates for many of the actions were obtained from knowledgeable sources based on current information. Estimates are subject to change due to specific details of specific projects.

- Potential sources of funding (discussed below).

- The primary hazard being addressed.

- The goal corresponding to the action.

As mentioned above, jurisdictions and entities integrally involved in the planning for disasters due to wide ranging implications to them include townships and most utility providers. Some utility providers were represented on the PDM Planning Team. Each utility provider was asked individually to submit their own mitigation actions. The main mitigation activity proposed by electric utility providers was the burying of overhead lines in rural areas of the county.

Township supervisors were asked to identify potential mitigation projects. Each individual township was provided maps upon which they were asked to identify potential mitigation activities and vulnerable roads or infrastructure. Primarily these activities included replacing culverts with larger culverts, elevating or rip-rapping roads, and reconstructing roads. Not all townships submitted the maps with potential activities; however the appendix includes maps of vulnerable sites and potential mitigation actions proposed by the townships in the County.

Particular attention needs to be paid to sources of funding for the actions. Given the existing financial reality of very tight county and municipal budgets, some of the proposed actions realistically cannot be implemented without substantial grant assistance. With such assistance, it is likely that many of the high priority projects can be undertaken without placing an onerous burden on local budgets. Resources for some of the actions available from FEMA through the South Dakota Office of Emergency Management include the Hazard Mitigation Grant Program, Pre-Disaster Mitigation grant program, and Flood Mitigation Assistance grant programs. Other possible sources of funding include:

Grant and loan programs/sources

- Community Development Block Grant program

- Economic Development Administration

- FEMA Assistance to Firefighters Grant program

- South Dakota Dept of Environment and Natural Resources

- South Dakota Dept of Transportation

- US Department of Agriculture Rural Development Office

Local resources

- General obligation bonds

- Revenue bonds

- Tax Increment Financing (TIF) districts

Table 5.13:  Proposed Mitigation Activities

| CLARK COUNTY PROBLEM STATEMENTS | CLARK COUNTY ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improve training and response by Emergency Responders across the County | Conduct additional Training sessions for Emergency Management Personnel | High | Medium | Clark County Emergency Management | N/A | City, USDA, CDBG, FD | All Hazards | Improve public safety during severe weather |
| Improve safety by conducting assessment of Storm Shelters | Assess all current storm shelters for readiness during weather event | High | Short | Clark County Emergency Management | N/A | HMGP/OEM, City, USDA | All Hazards | Improve public safety during severe weather |
| Existing storm shelters do not sufficiently serve the need of County/City of Clark residents | Construct a new storm shelter | High | Medium | City of Clark Council | N/A | HMGP/OEM, City, USDA | Severe Weather Hazards | Improve public safety of vulnerable populations during severe weather |

| CLARK COUNTY PROBLEM STATEMENTS | CLARK COUNTY ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Identify areas of high risk and develop strategies to mitigate those risks. | Develop inventories of at-risk buildings and infrastructure and prioritize mitigation projects. | Medium | Ongoing | County Emergency Management Director | Unknown | County | All | Improve public safety during hazardous conditions |
| Educate County residents regarding risks, vulnerability and mitigation activities for hazardous events | Periodic newspaper articles Severe Weather Awareness, Winter Weather Awareness and Fire Prevention Weeks | Medium | Ongoing | Clark County Emergency Management | >$1000 | County | All | Improve public safety during hazardous conditions |
| Identify areas prone to repetitive flooding and provide improved drainage | Identify potential areas for improvement of drainage management systems | Medium | Ongoing | County Emergency Management Director/Clark County Commission | Unknown | County and Municipal | Flooding | Reduce flooding and improve water flow throughout the County |
| CLARK COUNTY PROBLEM STATEMENTS | CLARK COUNTY ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| Continue planned upgrades to the Clark Airport | Identify improvements to the Clark Airport | Medium | Ongoing | County/Airport Manager | Unknown | County | Severe Weather | Continue operation through power outages/severe weather |

| CITY OF CLARK PROBLEM STATEMENTS | CITY OF CLARK ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Improve training and response by Emergency Responders across the City | Conduct additional Training sessions for Emergency Management Personnel | High | Medium | Clark County Emergency Management/City Council/Clark Police and Fire Department | N/A | City, USDA, CDBG, FD | All Hazards | Improve public safety during severe weather |
| Improve safety by conducting assessment of Storm Shelters | Assess all current storm shelters for readiness during weather event | High | Short | City Council | N/A | HMGP/OEM, City, USDA | All Hazards | Improve public safety during severe weather |
| No back-up generator available for use at Water and Wastewater Treatment Facilities | Purchase a new back-up generator | High | Short | Clark City Council | Unknown | City, HMGP, CDBG, FD | Severe Weather | Continue operation through power outages/severe weather |
| Identify areas prone to repetitive flooding and provide improved drainage | Identify potential areas for improvement of drainage management systems | Medium | Ongoing | City Council/Public Works Department | Unknown | HMGP/City | Flooding | Reduce flooding and improve water flow throughout the County |
| CITY OF CLARK PROBLEM STATEMENTS | CITY OF CLARK ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| Existing Water Tower is too old to repair and in disrepair | Construct new Water Tower | High | Medium | Water Superintendent | $1,000,000 | HMGP, State and Local Funds | Preventative | Ensure safe drinking water and water capacity |
| 7th Ave & Smith Street is prone to flooding | Install storm water drainage system | Medium | Medium | Street Superintendent | $42,000 | Local and State Funds | Flooding | Improve public safety during a flooding event |
| Drainage on the north side of the City is not sufficient to handle flooding | Construct drainage ditches and retention ponds as needed | Medium | Medium | Street Superintendent | $5,000 | Local and State Funds | Flooding | Improve public safety during a flooding event |

| TOWN OF BRADLEY PROBLEM STATEMENTS | TOWN OF BRADLEY ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No back-up generator available for use at the Community Center | Purchase a new back-up generator | High | Short | Town Board | N/A | HMGP, CDBG, FD | Severe Weather | Continue operation through power outages/severe weather |
| No emergency supplies are available at the community center in the event of severe weather | Purchase emergency supplies | Medium | Short | Town Board | $10,000 | HMGP, CDBG, FD | All Hazards | Provide necessary items during severe weather |
| Bradley Fire Department lacks necessary tools and supplies to assist volunteer firefighters | Purchase tools and supplies as needed to increase firefighting capabilities | Medium | Medium | Fire Chief | $20,000 | Local, AFG, BHS | Fire | Provide Bradley Fire Department with all necessary tools and supplies to effectively mitigate fires. |

| TOWN OF GARDEN CITY PROBLEM STATEMENTS | TOWN OF GARDEN CITY ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Existing warning siren is not sufficiently serving the need of town residents | Purchase and install a new storm warning siren. | High | Medium | Town Board | $50,000 | HMGP/OEM, City, USDA | Severe Weather Hazards | Improve public safety during severe weather |
| Garden City does not have a central water supply system | Connect to Clark Rural Water System | Medium | Medium | Town Board | $450,000 | Local, State and Federal Funds | All Hazards | Provide reliable water supply to Garden City |
| Wastewater lagoon shorelines are exposed to flooding | Place Rip Rap around the lagoon(s) | Low | Medium | Town Board | $25,000 | Local, State and Federal Funds | Flooding | Reduce potential of flooding |
| Garden City Fire Department lacks necessary tools and supplies to assist volunteer firefighters | Purchase tools and supplies as needed to increase fire-fighting capabilities | Medium | Medium | Fire Chief | $20,000 | Local, AFG, BHS | Fire | Provide GCFD with all necessary tools and supplies to effectively mitigate fires. |

| TOWN OF NAPLES PROBLEM STATEMENTS | TOWN OF NAPLES ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hollister Ave is prone to flooding | Road Repair/Culvert Placements | Medium | Medium | Naples Town Board | N/A | Local and State Funds | Flooding | Improve public safety during a flooding event |
| Town does not have a Storm Shelter | Construction of storm shelter in town | Low | Long | Naples Town Board | N/A | HMGP/OEM, City, USDA | Severe Storms and Tornado | Improve public safety during severe weather |
| No back-up generator available for use in town | Purchase a new back-up generator | High | Short | Naples Town Board | N/A | HMGP, CDBG, FD | Severe Weather | Continue operation through power outages/severe weather |
| No emergency supplies are available in the event of severe weather | Purchase emergency supplies | Medium | Short | Naples Town Board | $10,000 | HMGP, CDBG, FD | All Hazards | Provide necessary items during severe weather |

| TOWN OF RAYMOND PROBLEM STATEMENTS | TOWN OF RAYMOND ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Existing warning siren is not sufficiently serving the need of town residents | Purchase and install a new storm warning siren. | High | Medium | Raymond Town Board | $50,000 | HMGP/OEM, City, USDA | Severe Weather Hazards | Improve public safety during severe weather |
| Water Supply Infrastructure is outdated | Install new water lines, meters, and undertake water tower repairs | High | Long-term | Raymond Town Board | $1,000,000 | HMGP, CDBG, FD | All Hazards | Provide reliable water supply to Raymond |

| TOWN OF VIENNA PROBLEM STATEMENTS | TOWN OF VIENNA ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main St and Clark Ave are prone to flooding | Road Repair/Culvert Placements/Storm Sewer | Medium | Medium | Vienna Town Board | N/A | Local and State Funds | Flooding | Improve public safety during a flooding event |
| No back-up generator available for use at the Town/Community Hall | Purchase a new back-up generator | High | Short | Vienna Town Board | N/A | HMGP, CDBG, FD | Severe Weather | Continue operation through power outages/severe weather |
| No emergency supplies are available at the Town/Community hall in the event of severe weather | Purchase emergency supplies | Medium | Short | Naples Town Board | $10,000 | HMGP, CDBG, FD | All Hazards | Provide necessary items during severe weather |

| CITY OF WILLOW LAKE PROBLEM STATEMENTS | CITY OF WILLOW LAKE ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| City does not have a Storm Shelter at City Park | Construction of Storm Shelter at City Park | Low | Long | Willow Lake City Council | N/A | HMGP/OEM, City, State | Severe Storms and Tornado | Improve public safety during severe weather |
| Storm Sewer and Wastewater Lines have not been expanded into new areas of residential development | Installation and maintenance of utilities in new areas of development | Medium | Medium | Willow Lake City Council | N/A | HMGP/OEM, City, USDA | All Hazards | to which utility interruptions affect areas during severe weather situations |
| Water Supply Infrastructure is outdated | Install new water lines, meters, and undertake water tower repairs | High | Long-term | Willow Lake City Council | $1,000,000 | HMGP, CDBG, FD | All Hazards | Provide reliable water supply to Willow Lake |
| No emergency supplies are available at the Community Center in the event of severe weather | Purchase emergency supplies | Medium | Short | Willow Lake City Council | $10,000 | HMGP, CDBG, FD | All Hazards | Provide necessary items during severe weather |

| UTILITIES PROBLEM STATEMENTS | UTILITIES ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Overhead lines are vulnerable to freezing rai/sleet/ice | Bury powerlines where feasible | High | Medium | Codington-Clark | Depending on type of line and construction method | FEMA-HMGP, RUS, Utility Funds | Severe Winter Weather Hazards | Reduce the extent to which utility interruptions affect areas during severe weather situations |
| Overhead lines are vulnerable to ice and high wind events | Bury powerlines where feasible | High | Medium | Codington-Clark | Depending on type of line and construction method | FEMA-HMGP, RUS, Utility Funds | Severe Winter and Summer Weather Hazards | Reduce the extent to which utility interruptions affect areas during severe weather situations |
| Overhead lines are vulnerable to high wind events | Bury powerlines where feasible | High | Medium | Codington-Clark | Depending on type of line and construction method | FEMA-HMGP, RUS, Utility Funds | Severe Winter and Summer Weather Hazards | Reduce the extent to which utility interruptions affect areas during severe weather situations |
| UTILITIES PROBLEM STATEMENTS | UTILITIES ACTIONS | PRIORITY RATING | TIMEFRAME | CONTACT | COST | FUNDING SOURCE | HAZARD | GOAL |
| Overhead lines are vulnerable to flooding | Bury or rebuild overhead lines away from flood prone areas | Medium | Medium | Codington-Clark | Depending on type of line and construction methods | FEMA-HMGP, RUS, Utility Funds | Flooding | Reduce the extent to which utility interruptions affect areas during severe weather situations |

Figure 5.1: Clark County Potential Mitigation

Figure 5.2: Town of Bradley Potential Mitigation Project Map

Figure 5.3: City of Clark Potential Mitigation Project Map

Figure 5.4: Town of Garden City Potential Mitigation Project Map

Figure 5.5: Town of Naples Potential Mitigation Project Map

Figure 5.6: Town of Raymond Potential Mitigation Project Map

Figure 5.7: Town of Vienna Potential Mitigation Project Map

Figure 5.8 City of Willow Lake Potential Mitigation Project Map

IMPLEMENTATION OF MITIGATION ACTIONS

Requirement 201.6(c)(4)(ii).  Local Mitigation Plan Review Tool – C6.

Requirement 201.6(d)(3).  Local Mitigation Plan Review Tool – D3.

Upon adoption of the updated Clark County PDM, each jurisdiction will become responsible for implementing its own mitigation actions. The planning required for implementation is the sole responsibility of the local jurisdictions and private businesses that have participated in the PDM update. All of the municipalities have indicated that they do not have the financial capability to move forward with projects identified in the PDM at this time, however, all will consider applying for funds through the State and Federal Agencies once such funds become available. If and when the municipalities are able to secure funding for the mitigation projects, they will move forward with the projects identified. A benefit cost analysis will be conducted on an individual basis after the decision is made to move forward with a project.

The 2004 PDM was the first approved mitigation plan that the County has ever had on file. At the time the PDM was drafted it met the requirements for an approved mitigation plan. Clark County updated the original PDM plan in 2013. This plan met the requirements for the 2008 Local Mitigation Plan Review Crosswalk. The County updated their PDM plan in Summer of 2013.  The 2013 PDM update consisted of an All Hazards Mitigation Plan covering natural and manmade hazards. This plan met the requirements of the 2011 Local Mitigation Plan Review Tool. The plan was approved by FEMA. Information from the 2013 PDM plan was incorporated during the drafting of the 2018 PDM plan update. The FEMA approved methodology and format utilized for the 2018 Clark County PDM update is similar to counties neighboring Clark County.

CHAPTER 6

PLAN MAINTENANCE

MONITORING, EVALUATING, AND UPDATING THE PLAN

Requirement 201.6(c)(4)(ii).  Local Mitigation Plan Review Tool – C6.

The County and all of the participating local jurisdictions thereof will incorporate the findings and projects of the PDM in all planning areas as appropriate. Periodic monitoring and reporting of the PDM is required to ensure that the goals and objectives for the County PDM are kept current and that local mitigation efforts are being carried out. Communities will establish an annual review of projects and infrastructure listed in the plan. As funding becomes available, projects are completed, or the inevitable new project needs to be added, communities will report to the Clark County Emergency Management Director. Communities should adopt a schedule which corresponds with the annual report of the Emergency Management Director to the County Commissioners in November of each year.

During the process of implementing mitigation strategies, the county or communities within the county may experience lack of funding, budget cuts, staff turnover, and/or a general failure of projects. These scenarios are not in themselves a reason to discontinue and fail to update the PDM. A good plan needs to provide for periodic monitoring and evaluation of its successes and failures and allow for appropriate changes to be made.

CONTINUED PUBLIC PARTICIPATION/INVOLVEMENT

Requirement 201.6(c)(4)(iii).  Local Mitigation Plan Review Tool – A5.

Requirement 201.6(c)(4)(ii).  Local Mitigation Plan Review Tool – C6.

During interim periods between the five-year re-write, efforts will be continued to encourage and facilitate public involvement and input. The PDM will be available for public view and comment at the Clark County Emergency Management Office located in the Clark County Courthouse and the First District Association of Local Governments office. The PDM will also be available for review on the Clark County website and on the First District Association of Local Governments homepage (www.1stdistrict.org). Comments will always be received whether orally, written or by e-mail.

All ongoing workshops and trainings will be open to the public and appropriately advertised. Ongoing press releases and interviews will help disseminate information to the general public and encourage participation.

As implementation of the mitigation strategies continues in each local jurisdiction, the primary means of public involvement will be the jurisdiction’s own public comment and hearing process.  State law as it applies to municipalities and counties requires this as a minimum for many of the proposed implementation measures. Effort will be made to encourage cities, towns and counties to go beyond the minimum required to receive public input and engage stakeholders.

ANNUAL REPORTING PROCEDURES

Requirement 201.6(c)(4)(ii).  Local Mitigation Plan Review Tool – C6.

The PDM shall be reviewed annually, as required by the County Emergency Management Director, or as the situation dictates such as following a disaster declaration. The Clark County Emergency Management Director will review the PDM annually in November and ensure the following:

- The County Elected body will receive an annual report and/or presentation on the implementation status of the PDM;

- The report will include an evaluation of the effectiveness and appropriateness of the mitigation actions proposed in the PDM; and

- The report will recommend, as appropriate, any required changes or amendments to the PDM.

FIVE-YEAR PDM REVIEW

Requirement 201.6(c)(4)(i).  Local Mitigation Plan Review Tool – A6.

Requirement 201.6(c)(4)(ii).  Local Mitigation Plan Review Tool – C6.

Every five years the PDM will be reviewed and a complete update will be initiated. All information in the PDM will be evaluated for completeness and accuracy based on new information or data sources. New property development activities will be added to the PDM and evaluated for impacts. New or improved sources of hazard related data will also be included.

In future years, if the County relies on grant dollars to hire a contractor to write the PDM update, the County will initiate the process of applying for and securing such funding in the third year of the PDM to ensure the funding is in place by the fourth year of the PDM. The fifth year will then be used to write the PDM update, which in turn will prevent any lapse in time where the county does not have a current approved PDM on file.

The goals, objectives, and mitigation strategies will be readdressed and amended as necessary based on new information, additional experience and the implementation progress of the PDM. The approach to this PDM update effort will be essentially the same as the one used for the original PDM development.

The Emergency Management Director will meet with the PDM Planning Team for review and approval prior to final submission of the updated PDM.

PLAN AMENDMENTS

Requirement 201.6(c)(4)(ii).  Local Mitigation Plan Review Tool – C6.

PDM amendments will be considered by the Clark County Emergency Management Director, during the PDM’s annual review to take place the end of each county fiscal year. All affected local jurisdictions (cities, towns, and counties) will be required to hold a public hearing and adopt the recommended amendment by resolution prior to considerations by the PDM Planning Team.

INCORPORATION INTO EXISTING PLANNING MECHANISMS

Requirement 201.6(B)(3).  Local Mitigation Plan Review Tool – A4.

All towns with existing comprehensive land use plans will review mitigation projects annually when reviewing their comprehensive land use plan, as is recommended in each of their plans.  In addition, all municipalities, including the towns without comprehensive land use plans, will consider the mitigation requirements, goals, actions, and projects when it considers and reviews the budget and other existing planning documents. Preparation of the budget is an opportune time to review the plan since municipalities are required by state law to prepare budgets for the upcoming year and typically consider any expenditure for the upcoming year at that time.

The local jurisdictions will post a permanent memo to their files as a reminder for them to incorporate their annual review of the mitigation actions identified into the budget preparation process. This does not require the projects be included in the budget, it merely serves as a reminder to the City officials that they have identified mitigation projects in the PDM that should be considered if the budget allows for it.

POTENTIAL FUNDING SOURCES

Although all mitigation techniques will likely save money by avoiding losses, many projects are costly to implement. None of the local jurisdictions have the funds available to move forward with mitigation projects at this time; thus, the Potential Funding Sources section was included so that the local jurisdictions can work towards securing funding for the projects. Inevitably, due to the small tax base and small population most of the local jurisdictions do not have the ability to generate enough revenue to support anything beyond the basic needs of the community. Thus, mitigation projects will not be completed without a large amount of funding support from State or Federal programs.

The County jurisdictions will continue to seek outside funding assistance for mitigation projects in both the pre- and post-disaster environment. Primary Federal and State grant programs have been identified and briefly discussed, along with local and non-governmental funding sources, as a resource for the local jurisdictions

Federal

The following federal grant programs have been identified as funding sources which specifically target hazard mitigation projects:

Title: Pre-Disaster Mitigation Program Agency: Federal Emergency Management Agency

Through the Disaster Mitigation Act of 2000, Congress approved the creation of a national program to provide a funding mechanism that is not dependent on a Presidential Disaster Declaration. The Pre-Disaster Mitigation (PDM) program provides funding to states and communities for cost-effective hazard mitigation activities that complement a comprehensive mitigation program and reduce injuries, loss of life, and damage and destruction of property. The funding is based upon a 75% Federal share and 25% non-Federal share. The non-Federal match can be fully in-kind or cash, or a combination. Special accommodations will be made for “small and impoverished communities”, who will be eligible for 90% Federal share/10% non-Federal. FEMA provides PDM grants to states that, in turn, can provide sub-grants to local governments for accomplishing the following eligible mitigation activities: State and local hazard mitigation planning, Technical assistance (e.g. risk assessments, project development), Mitigation Projects, Acquisition or relocation of vulnerable properties, Hazard retrofits, Minor structural hazard control or protection projects Community outreach and education (up to 10% of State allocation)

Title: Flood Mitigation Assistance Program Agency: Federal Emergency Management Agency

FEMA’s Flood Mitigation Assistance program (FMA) provides funding to assist states and communities in implementing measures to reduce or eliminate the long-term risk of flood damage to buildings, manufactured homes and other structures insurable under the National Flood Insurance Program (NFIP). FMA was created as part of the National Flood Insurance Reform Act of 1994 (42 USC 4101) with the goal of reducing or eliminating claims under the NFIP. FMA is a pre-disaster grant program and is available to states on an annual basis. This funding is available for mitigation planning and implementation of mitigation measures only and is based upon a 75% Federal share/25% non-Federal share. States administer the FMA program and are responsible for selecting projects for funding from the applications submitted by all communities within the state. The state then forwards selected applications to FEMA for an eligibility determination. Although individuals cannot apply directly for FMA funds, their local government may submit an application on their behalf.

Title: Repetitive Flood Claims Program Agency: Federal Emergency Management Agency

FEMA’s Repetitive Flood Claims (RFC) grant program was authorized by the Bunning-Bereuter-Blumenauer Flood Insurance Reform Act of 2004 (P.L. 108–264), which amended the National Flood Insurance Act (NFIA) of 1968 (42 U.S.C. 4001, et al). Up to $10 million is available annually for FEMA to provide RFC funds to assist States and communities reduce flood damages to insured properties that have had one or more claims to the National Flood Insurance Program (NFIP). FEMA may contribute up to 100 percent of the total amount approved under the RFC grant award to implement approved activities, if the Applicant has demonstrated that the proposed activities cannot be funded under the Flood Mitigation Assistance (FMA) program.

Title: Hazard Mitigation Grant Program Agency: Federal Emergency Management Agency

The Hazard Mitigation Grant Program (HMGP) was created in November 1988 through Section 404 of the Robert T. Stafford Disaster Relief and Emergency Assistant Act. The HMGP assists states and local communities in implementing long-term mitigation measures following a Presidential disaster declaration. To meet these objectives, FEMA can fund up to 75% of the eligible costs of each project. The state or local cost-share match does not need to be cash; in-kind services or materials may also be used. With the passage of the Hazard Mitigation and Relocation Assistance Act of 1993, federal funding under the HMGP is now based on 15% of the federal funds spent on the Public and Individual Assistance programs (minus administrative expenses) for each disaster. The HMGP can be used to fund projects to protect either public or private property, so long as the projects in question fit within the state and local governments overall mitigation strategy for the disaster area and comply with program guidelines. Examples of projects that may be funded include the acquisition or relocation of structures from hazard-prone areas, the retrofitting of existing structures to protect them from future damages; and the development of state or local standards designed to protect buildings from future damages. Eligibility for funding under the HMGP is limited to state and local governments, certain private nonprofit organizations or institutions that serve a public function, Indian tribes and authorized tribal organizations. These organizations must apply for HMPG project funding on behalf of their citizens. In turn, applicants must work through their state, since the state is responsible for setting priorities for funding and administering the program.

Title: Public Assistance (Infrastructure) Program, Section 406 Agency: Federal Emergency Management Agency

FEMA’s Public Assistance Program, through Section 406 of the Robert T. Stafford Disaster Relief and Emergency Assistance Act, provides funding to local governments following a Presidential Disaster Declaration for mitigation measures in conjunction with the repair of damaged public facilities and infrastructure. The mitigation measures must be related to eligible disaster related damages and must directly reduce the potential for future, similar disaster damages to the eligible facility. These opportunities usually present themselves during the repair/replacement efforts. Proposed projects must be approved by FEMA prior to funding. They will be evaluated for cost effectiveness, technical feasibility and compliance with statutory, regulatory and executive order requirements. In addition, the evaluation must ensure that the mitigation measures do not negatively impact a facility’s operation or risk from another hazard. Public facilities are operated by state and local governments, Indian tribes or authorized tribal organizations and include: *Roads, bridges & culverts *Water, power & sanitary systems *Draining & irrigation channels *Airports & parks *Schools, city halls & other buildings Private nonprofit organizations are groups that own or operate facilities that provide services otherwise performed by a government agency and include, but are not limited to the following: *Universities and other schools *Power cooperatives & other utilities *Hospitals & clinics *Custodial care & retirement facilities *Volunteer fire & ambulance *Museums & community centers

Title: SBA Disaster Assistance Program Agency: US Small Business Administration

The SBA Disaster Assistance Program provides low-interest loans to businesses following a Presidential disaster declaration. The loans target businesses to repair or replace uninsured disaster damages to property owned by the business, including real estate, machinery and equipment, inventory and supplies. Businesses of any size are eligible; along with non-profit organizations. SBA loans can be utilized by their recipients to incorporate mitigation techniques into the repair and restoration of their business.

Title: Community Development Block Grants Agency: US Department of Housing and Urban Development

The community Development Block Grant (CDBG) program provides grants to local governments for community and economic development projects that primarily benefit low- and moderate-income people. The CDBG program also provides grants for post-disaster hazard mitigation and recovery following a Presidential disaster declaration. Funds can be used for activities such as acquisition, rehabilitation or reconstruction of damaged properties and facilities and for the redevelopment of disaster areas.

#### Local

Local governments depend upon local property taxes as their primary source of revenue. These taxes are typically used to finance services that must be available and delivered on a routine and regular basis to the general public. If local budgets allow, these funds are used to match Federal or State grant programs when required for large-scale projects.

#### Non-Governmental

Another potential source of revenue for implementing local mitigation projects are monetary contributions from non-governmental organizations, such as private sector companies, churches, charities, community relief funds, the Red Cross, hospitals, Land Trusts and other non-profit organizations.

APPENDIX

Appendix A - Resolution of Adoption by Jurisdiction

Appendix B - PDM Planning Team Agendas, Sign-in Sheets, and Minutes Appendix C - Community Meeting Agendas and Sign-in Sheets

Appendix D - Hazard Identification/Vulnerability Worksheets

Appendix E - Township Vulnerable and Potential Mitigation Project Site Maps

Appendix F - Codington-Clark Electric Co-Op: Critical Infrastructure/Overhead Power Lines Map Guide

Appendix G - Comprehensive Land Use Maps

Appendix H - Review of 2013 PDM Mitigation Project Implementation

Appendix I - References

Appendix A

Resolution of Adoption by Jurisdiction

Clark County Resolution

Bradley Resolution

Clark (City) Resolution

Garden City Resolution

Naples Resolution

Raymond Resolution

Vienna Resolution

Willow Lake Resolution

Codington-Clark Electric Co-Op Resolution

Appendix B

PDM Planning Team Agendas, Sign-in Sheets and Minutes

Kickoff Meeting Agenda

Clark County Pre-Disaster Mitigation Plan

Kickoff Meeting

7:00 p.m. Tuesday, August 28th, 2018

Clark County Courthouse Basement

Agenda

- Introduction of team members

- What is mitigation planning

- Why is Clark County updating the Pre-Disaster Mitigation Plan?

- Review plan components

- Review timeline/scope

Kickoff Meeting Sign in Sheet

Kickoff Meeting Minutes

RESERVED

Kickoff Meeting Minutes

Clark County Pre-Disaster Mitigation Plan Team Kick-Off Meeting

August 28, 2018

Clark County Courthouse Basement

14 individuals were in attendance:

- Bob Johnson, Codington-Clark Electric Co-Op

- Rob McGraw, Clark County Sheriff’s Office

- Jeremy Wellnitz, Clark Police Chief

- Michael Gravning, Clark County Emergency Management

- Heidi Madsen, City of Willow Lake

- Christine Tarbox, Clark County Auditor

- Joyce Hallauer, SD DOH Healthcare Coalition

- Jeff Seefeldt, Clark Fire Department

- Scott Drexler, City of Raymond

- Doug Yexley, Bradley Fire Department

- Russ Hurlbert, Raymond Fire Department

- Luke Muller, First District Association of Local Governments

- Todd Kays, First District Association of Local Governments

- Thomas Nealon, First District Association of Local Governments

Clark County Emergency Management Director Michael Gravning welcomed those in attendance and had team members introduce themselves and what entity they represented. Gravning then introduced Planner Todd Kays of the First District Association of Local Governments.

Kays provided an overview of what is mitigation planning and why the county is required to update their Pre-Disaster Mitigation (PDM) Plan. Maag also provided a review of the components to be included within the plan (risk assessment, vulnerability, goals, proposed mitigation actions).

Luke Muller, Planner at First District Association of Local Governments led the Planning Team members through the risk assessment worksheets process to identify hazards and rate the County’s vulnerability to these hazards. Planning Team representatives provided information regarding mitigation activities within their own respective entities. A general review of the existing Pre-Disaster Mitigation Plan was started by defining work responsibilities for all parties involved in the process. The First District will be doing background and research, and the PDM Team provides oversight and guidelines throughout the process. The timeline and scope of project were reviewed.

Meeting adjourned at 8:30 p.m. Date and time for the next meeting to be scheduled later in the year.

Minutes recorded by Thomas Nealon.

2nd PDM Meeting Agenda

2nd PDM Meeting Sign in Sheet

2nd Meeting Minutes

Clark County Pre-Disaster Mitigation Team Meeting Minutes

November 13, 2018

Clark County Courthouse Basement

7:00 p.m.

Four team members were in attendance. Team meeting began with introductions.

Thomas Nealon of the First District provided a brief review of previous meetings and plan development activities conducted since the last Team meeting in August 2018.

Nealon provided a summary and review of the draft Clark County Pre-Disaster Mitigation Plan.

Nealon discussed plan authority and purpose. He provided an overview of the community profile information and information sources. Maag covered the multi-jurisdictional plan and plan participation requirements. The plan development process was discussed in more detail.

Nealon provided an in-depth discussion of risk assessment and vulnerability in Clark County. He covered the risk assessments conducted with the communities of Bradley, Clark, Garden City, Naples, Raymond, Vienna, and Willow Lake. The risk assessment review with those entities dealt with identification of potential hazards, generating a hazard profile, and vulnerability assessment. Nealon discussed vulnerabilities and potential losses in the county. He went over the administrative and technical capabilities within Clark County.

The Team reviewed and revised goals and objectives of the previous PDM Plan. The Team agreed to incorporate the new goals and objectives into the updated plan.

Goals and Objectives

- Reduce the loss of life, property, infrastructure, critical facilities, cultural resources and impacts from severe weather, flooding and other natural disasters.

- Improve public safety during severe weather, flooding and other natural disasters.

- Improve the County’s emergency preparedness, disaster response and recovery capabilities.

Severe Weather, Flooding, Fire and Drought Administration.

Greg Maag discussed potential mitigation projects throughout the county and communities.

Nealon explained the plan maintenance requires for the next five years.

Discussion and questions occurred during and after the summary process.

Consensus of the Team was to spend more time on individual review of the document and to provide First District staff with any corrections/updates.

Meeting adjourned at 8:05 p.m., with a tentative date of the final meeting to be in December 27, 2018.

Minutes recorded by Greg Maag

3rd Meeting Agenda

Clark County Pre-Disaster Mitigation Plan

Mitigation Planning Team Meeting #3

7:00 p.m.   January 10, 2019

Clark County Courthouse Basement

Agenda

- Final Review of PDM Plan

- Recommendation of Approval and Submission to FEMA

3rd Meeting Sign in Sheet

3rd Meeting Minutes

Clark County Pre-Disaster Mitigation Team

PDM Meeting #3

January 10, 2019

Clark County Courthouse Basement

7:00 p.m.

Nine people were in attendance:

- Eight PDM team members

- Thomas Nealon, First District Association of Local Governments

Thomas Nealon of First District provided an overview of the changes to the Pre-Disaster Mitigation Plan received since the last meeting. The draft plan was posted on the First District and Clark County websites on November 9, 2018.  Plan discussion and comments were received from those in attendance.

Motion by McGraw, second by Hallauer to approve the final draft of the plan and submit to State of South Dakota and FEMA for their review.  Motion passed unanimously.

Nealon reviewed the community and county adoption process after approval by FEMA.

Meeting adjourned at 7:15 p.m.

Minutes recorded by Thomas Nealon

Appendix C

Community Meeting Agendas, Sign-in Sheets and Minutes

Appendix C includes Agendas, “Sign-in Sheets” and Minutes from the initial meetings held at the community level for the Clark County Pre-Disaster Mitigation Plan. Meetings were held at the regular monthly meetings for the following Towns:

Town	Date

Bradley			September 19th, 2018

Clark 				September 9th, 2018

Garden City			September 20th, 2018

Naples				November 5th, 2018

Raymond 			November 5th, 2018

Vienna				October 11, 2018

Willow Lake 			October 8, 2018

At all of the previously described meetings, each individual in attendance was asked to identify the probability of each specific hazard’s occurrence. Following discussion on each individual hazard, Board members categorized these hazards as high probability to occur, low probability to occur, or unlikely to occur. The result was recorded on a master sheet for each town.  Next, each individual in attendance was asked to identify the town’s vulnerability to each specific hazard. Following discussion on each individual hazard, Board members classified the town’s vulnerability to each hazard as high vulnerability, low vulnerability, or noted that the hazard was not a hazard in the jurisdiction. The result was recorded on a master sheet for each town. Following the hazard identification and vulnerability exercises the governing body was asked to rate the level to which they agree with the goals of the Pre-Disaster Mitigation Plan. Finally, the Town Board was asked to identify critical infrastructure within the community. All master sheets and infrastructure lists compiled at those meetings can be found in Appendix E. A master infrastructure list was compiled for each town Table 4.16.

Town of Bradley

Bradley Sign in Sheet

Bradley Minutes

City of Clark

Clark Sign in Sheet

Clark Minutes

Town of Garden City

Garden City Sign in Sheet

Garden City Minutes

Naples Agenda

Naples Sign in Sheet

Naples Minutes

Raymond Agenda

Raymond Sign in Sheet

RAYMOND MINUTES

VIENNA AGENDA

Vienna Sign in Sheet

‘

VIENNA MINUTES

City of Willow Lake

Willow Lake Sign in Sheet

Willow Lake Minutes

Appendix D - Hazard Identification/Vulnerability Worksheets

Appendix D includes master worksheets for Hazard Identification and Vulnerability for jurisdictions compiled as described in Appendix C.   Lists were gathered by Codington-Clark Electric Co-Op, Clark Rural Water System, and Clark County Emergency Management Staff for their respective entities and at meetings for the other communities as described below:

Entity	Date

Clark County PDM Planning Team August 28, 2018

Bradley	September 19th, 2018

Clark	September 9th, 2018

Garden City	September 20th, 2018

Naples	November 5th, 2018

Raymond 	November 5th, 2018

Vienna	October 11th, 2018

Willow Lake	October 8th, 2018

Master worksheets for Hazard Identification and Vulnerability for jurisdictions and utilities (multiple was submitted for Clark County) below.

Town of Bradley

City of Clark

Town of Garden City  

Town of Naples 

Town of Raymond

Town of Vienna

City of Willow Lake 

Clark County

Codington-Clark Electric Co-Op

Clark County Commission

COUNTY COMMISSION AND ZONING

Clark County Zoning

Appendix E

Township Vulnerable and Potential Mitigation Project Site Maps

In September of 2018 First District mailed a request to the Township Clerk or Road Supervisor of every township in Clark County. They were requested to list any critical infrastructure and identify (on a map) any areas which are most vulnerable to natural hazards, specifically flooding.  It was assumed that any townships which did not respond to the information request had no critical infrastructure or vulnerable areas which may require mitigation activities. Of the 27 requests sent, eight were returned with vulnerable areas identified (see table below).

| Township | Response | Township | Response |
| --- | --- | --- | --- |
| Ash Township |  | Mount Pleasant Township | X |
| Blaine Township |  | Pleasant Township | X |
| Collins Township |  | Raymond Township |  |
| Cottonwood Township | X | Richland Township |  |
| Darlington Township |  | Rosedale Township |  |
| Day Township |  | Spring Valley Township | X |
| Eden Township | X | Thorp Township |  |
| Elrod Township | X | Warren Township |  |
| Fordham Township |  | Washington Township |  |
| Foxton Township |  | Woodland Township |  |
| Garfield Township |  |  |  |
| Hague Township | X |  |  |
| Lake Township |  |  |  |
| Lincoln Township |  |  |  |
| Logan Township |  |  |  |
| Maydell Township | X |  |  |
| Merton Township |  |  |  |

Ash Township

Blaine Township

Collins Township

Cottonwood Township

Darlington Township

Darlington Township

Day Township

Eden Township

Elrod Township

Fordham Township

Foxton Township

Garfield Township

Hague Township

Lake Township

Lincoln Township

Logan Township

Maydell Township

Merton Township

Mount Pleasant Township

Pleasant Township

Raymond Township

Richland Township

Rosedale Township

Spring Valley Township

Thorp Township

Warren Township

Washington Township

Woodland Township

Appendix F Codington-Clark Electric Co-Op Map Guide

Appendix F - Codington-Clark Electric Co-Op: Critical Infrastructure Map Guide

Appendix F - Codington-Clark Electric Co-Op: Critical Infrastructure/Overhead Power Lines Map Guide

Map 1

Map 2

Map 3

Map 4

Map 5

Map 6

Map 7

Map 8

Map 9

Map 10

Map 11

Map 12

Map 13

Map 14

Map 15

Map 16

Map 17

Map 18

Map 19

Map 20

Map 21

Map 22

Map 23

Map 23

Map 24

Map 25

Map 25

Map 26

Map 27

Appendix G – Comprehensive Land Use Maps

Appendix G – Comprehensive Land Use Maps

City of Clark

Town of Vienna

City of Willow Lake

Clark County

Appendix H– Review of 2013 PDM Mitigation Project Implementation

| COMMUNITY | POTENTIAL MITIGATION PROJECTS | HAZARD | INCLUDED IN 2018 PLAN? | STATUS |
| --- | --- | --- | --- | --- |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Review mutual aid agreements at the County and Jurisdictional Level | All Hazards | Yes | Ongoing |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Insure Clark County and Jurisdictional Emergency Operation Plans are current | All Hazards | Yes | Ongoing |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Training of Emergency Services for Severe Weather, Tornado Spotting, Hazardous Materials, Vehicle Safety Training, School and Assisted Living Planning | All Hazards | Yes | Ongoing |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Conduct Emergency Exercises to test Emergency Operation Plans | All Hazards | Yes | Ongoing |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Assess Previous Storm Shelters for use | Severe Weather | Yes – part of critical infrastructure identification | Ongoing |
| COMMUNITY | POTENTIAL MITIGATION PROJECTS | HAZARD | INCLUDED IN 2018 PLAN? | STATUS |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Identify new and secondary shelters in the County and Jurisdictions as needed | Severe Weather | Yes | Ongoing |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Develop a comprehensive mass shelter and care plan for the entire County | Severe Weather | No | No longer a priority. |
| Clark County | Ongoing maintenance of continuity of operations plan | All Hazards | Yes | Ongoing |
| Clark County, City of Clark, Town of Raymond, City of Willow Lake | Develop protocols to purchase food during sheltering e vents | All Hazards | No | No longer a priority |
| Clark County and City of Clark | Snow removal building, upgrade taxi ways and tarmac area. Propose new terminal | Winter Ice Storms | No | No longer a priority |
| Codington-Clark Electric Co-Op | Replacement of overhead lines affected by ice, water, and trees | Winter Ice Storms | Yes | Completed/Ongoing (See Appendix F) |
| Clark County | Continue severe weather awareness programs | All Hazards | Yes | Ongoing |
| COMMUNITY | POTENTIAL MITIGATION PROJECTS | HAZARD | INCLUDED IN 2018 PLAN? | STATUS |
| Clark County and City of Clark | Support the use of NOAA Weather Radios for all hazard events | All Hazards | No | No longer a priority |
| Clark County and City of Clark | Continue warning and evacuation procedures | All Hazards | Yes | Ongoing |
| Clark County and participating communities | Continue to participate in NFIP | Flooding | Yes | Ongoing |
| Clark County and participating communities | Establish Drainage Districts | Flooding | No | No longer a priority |
| City of Clark | Ditch Cleaning as needed affecting NE portion of city | Flooding | No | No longer a priority |
| Clark County | Work with non-participating jurisdictions to determine whether participation in NFIP is feasible | Flooding | Yes | Ongoing |
| Clark County | Identify roads that need to be elevated and culverts that need to be replaced. Bridge replacements that are deteriorated | Flooding | Yes | Ongoing/included in County Bridge Plan |

| COMMUNITY | POTENTIAL MITIGATION PROJECTS | HAZARD | INCLUDED IN 2018 PLAN? | STATUS |
| --- | --- | --- | --- | --- |
| City of Clark | Develop Water retention area to reduce degradation from flooding | Flooding | No | No longer a priority |
| City of Clark | Outreach to general public on dangers of flood and construction in floodplains. | Flooding | Yes | Ongoing |
| Town of Raymond | Develop drainage system to reduce flooding | Flooding | Yes | Ongoing |
| City of Willow Lake | Reducing flooding in an area on school grounds due to collapsed storm drainage line running from SD HWY 28 to Monroe Ave | Flooding | No | Completed |

Appendix I - References

City of Clark Comprehensive Land Use Plan, Zoning and Subdivision Ordinances – Ulteig, 2009

Comprehensive Land Use Plan for Clark County – First District Association of Local Governments, 2014

Local Hazard Mitigation Planning Tool – Federal Emergency Management Agency. 2011.

Clark County Multi-Hazard Mitigation Plan, 2018

Clark County Zoning Ordinance – First District Association of Local Governments, 2014

NFIP Flood Insurance Rate Maps and Community Status Book Report

State of South Dakota Hazard Mitigation Plan. South Dakota Office of Emergency Management.  2014.

City of Willow Lake Comprehensive Land Use Plan and Zoning Ordinance – First District Association of Local Governments, 2003

Town of Vienna Comprehensive Land Use Plan and Zoning Ordinance – First District Association of Local Governments, 2009